## Cost Certification Guideline
Connecticut Housing Finance Authority
Cost Certification Preparation Guideline
2020
This Guideline is Effective January 2020
I. Preface
This Guideline is intended to provide guidance to the owners, general contractors, and independent Certified Public Accountants (CPA) for the preparation and submission of cost certifications to the Connecticut Housing Finance Authority (CHFA). The guideline applies to all developments receiving funding through CHFA’s Multifamily Rental Housing Program, the Low-Income Housing Tax Credit (LIHTC) Program, or other multifamily financing programs.
II. Purpose
The purpose of the cost certification is to establish the total costs incurred by the general contractor and the owner to complete the development so that CHFA may determine at Final Closing the Total Development Costs of the development, the final principal amount of the CHFA loan(s), the final amount of the annual allocation of LIHTC, and the owner's equity in the development. For non-LIHTC developments, if applicable, CHFA will review the Mortgagor’s Cost Certification to establish the total costs incurred to complete the housing development.
The cost certification audits must be completed by an independent, third-party Certified Public Accountant (CPA) who is familiar with the requirements of Section 42 of the Internal Revenue Code (IRC).
Because of the complexity of the rules governing CHFA’s Multifamily Rental Housing and the LIHTC Programs, all participants are urged to seek appropriate legal and accounting advice regarding construction related matters, monthly draw requests, cost certifications and other matters associated with the disbursement of CHFA funds. Owners and general contractors may engage accounting and legal representation of their choice without CHFA approval, and are urged to do so at an early stage in the processing/underwriting of developments anticipated to be funded with CHFA financing and/or LIHTC.
Questions related to the General Contractor’s Cost Certification should be directed to Seema Malani via e-mail at seema.malani@chfa.org or via phone at 860-571-4296. Questions related to the Mortgagor’s-LIHTC Cost Certification should be directed to Maj Kabir via e-mail at maj.kabir@chfa.org or via phone at 860-571-4238.
Note: CHFA allows the General Contractor's and/or Mortgagor's-LIHTC Cost Certifications to be submitted in draft form. Owners and/or CPAs may submit the Excel Cost Certification workbook only for initial review by CHFA.
III. Requirements
All developments consisting of 10 or more units containing LIHTC, with or without CHFA financing, are required to complete General Contractor’s and Mortgagor’s-LIHTC Cost Certifications. The requirements for cost certifications may differ for non-LIHTC funded developments.
Within 180 days of Substantial Completion, the general contractor and the owner shall submit to CHFA the General Contractor’s and Mortgagor’s-LIHTC Cost Certifications.
The cost certification must be submitted on the current version of the CHFA cost certification forms that are included within this document. This document includes two separate lists of required documentation to be submitted with the General Contractor’s and Mortgagor’s-LIHTC Cost Certifications.
The General Contractor’s Cost Certification shall not be prepared by the same CPA preparing the Mortgagor’s-LIHTC Cost Certification. It is acceptable for the same CPA firm to prepare both certifications as long as different CPAs are preparing them.
If payables are noted on the cost certifications, then the general contractor and the owner/mortgagor shall submit Supplemental Cost Certification(s) acceptable to CHFA within 60-days of final closing.
Note: If there is more than one general contractor for any development, CHFA requires a separate General Contractor’s Cost Certification from each general contractor.
IV. General Contractor’s (G.C.) Cost Certification Instructions
For each Construction Division (Divisions 2 through 16) the CPA must submit a schedule of costs, which includes monies paid to vendor(s), as well as general requirements, builder’s overhead, builder’s profit-GMP fees, building permit and other fees, bond premium costs and CHFA approved change orders. The certification should include cost determinations for construction costs associated with the development including designated punch list items and allowances for seasonal work. Please note that the Project Cost Summary (PCS) shall be used as a source document for evaluating G.C. costs at Final Closing.
The G.C. Cost Certification must follow the |  | General Contractor's Certification of Actual Cost form
and be accompanied by the all the items listed on the |  |  | G.C. Cost Certification Checklist.
For developments with construction contract between owner and G.C. where the basis of payment is the Cost of the Work Plus a fee with a Guaranteed Maximum Price, CHFA recognized construction amount for cost certification purposes shall be the lesser of:
i. | The actual cash paid and to be paid at final closing, as reflected on the General Contractor’s Certificate of Actual Costs; or
ii. | The contract price under the construction contract, as reflected on the most recent approved PCS.
For reimbursement of costs associated with permit, other fees and bond premiums, the G.C. shall provide proof of payment, such as a paid receipt or paid invoice. The PCS submitted at Initial Closing or a 42M letter issued by CHFA shall be updated to reflect these actual incurred amounts.
CHFA-recognized general requirements, builder’s overhead and builder’s profit-GMP fees are calculated as a percentage of the CHFA recognized construction cost (Subtotal for Divisions 2-16). The percentage for general requirements, builder’s overhead and builder’s profit-GMP fees is computed based on the most recent approved PCS.
All CHFA-approved change orders will be added to the above-mentioned recognized construction cost. Additional bond and/or permit costs generated by the change order preparation and approval process during construction will be handled separately through a final change order at the completion of construction. The amount of actual cash paid or to be paid as described above shall be reduced by CHFA to the extent such amount includes any costs disallowed by CHFA in its review of the contractor’s certificate of actual cost.
Any hard cost savings realized during or at the end of the construction may be used for betterments to the project upon approval from CHFA. To use these savings for betterments to the project the savings will be added to the construction contingency via credit change orders. These savings will be controlled by the owner. Any cost saving agreement between Owner and GC must be disclosed to and approved by CHFA at the time of Initial Closing or a 42M letter is issued by CHFA. Note that CHFA will only recognize GMP savings for the GC to the extent that the builder’s profit does not exceed the maximum allowed by CHFA. All remaining hard cost savings will be allocated as described in the Multifamily Rental Housing Program Guideline, which is available on the CHFA website.
For developments with construction contract between owner and G.C. where the basis of payment is Stipulated Sum, CHFA recognized construction cost amount for cost certification shall be the contract price under the construction contract, as reflected on the most recent approved PCS, excluding costs for permit, other fees and bond premiums. For reimbursement of costs associated with permit, other fees and bond premiums, the GC shall provide proof of payment, such as a paid receipt or paid invoice. The PCS submitted at Initial Closing or a 42M letter issued by CHFA shall be updated to reflect these actual incurred amounts. Note that CHFA will only recognize builder’s profit to the extent that it does not exceed the maximum allowed by CHFA.
All CHFA-approved change orders will be added to the above-mentioned recognized construction cost. Additional bond and/or permit costs generated by the change order preparation and approval process during construction will be handled separately through a final change order at the completion of construction. The amount of actual cash paid or to be paid as described above, shall be reduced by CHFA to the extent that such amount includes any costs disallowed by CHFA in its review of the contractor’s certificate of actual cost.
The development owner must forward a copy of the CHFA approved G.C. Cost Data Sheet to the CPA that will prepare the Mortgagor’s-LIHTC cost certification. CHFA will recognize these construction costs on the Mortgagor’s-LIHTC cost certification.
V. Mortgagor’s-LIHTC Cost Certification Instructions
The Mortgagor's-LIHTC Cost Certification must be prepared by a third party independent CPA who is familiar with the requirements of Section 42 of the IRC, Technical Assistance Memorandum, Private Rulings (TAM) 200043015, 200043017, 200044004, and 200044005. The Mortgagor's-LIHTC Cost Certification must include the following statement signed by the CPA firm preparing the cost certification:
We acknowledge that we are familiar with Internal Revenue Service Technical Advice Memorandums (TAMs) numbered 200043015, 200043016, 200043017, 20044044 and 20044005.
The development budget approved as of the initial closing may be modified during the development process with the prior written consent of CHFA. The most recent development budget approved by CHFA shall serve as the basis for review and acceptance of required cost certifications. Owners are strongly advised to coordinate with CHFA to confirm that the appropriate development budget is used to complete the cost certifications.
Consistent with Section 42(m)(2) of the Internal Revenue Code and industry best practices, CHFA will only allocate the amount of LIHTC that are necessary to make a development financially feasible and viable, when considering all other sources of funding for the development.
The Mortgagor's-LIHTC cost certification must follow the |  |  | Mortgagor's-LIHTC Cost Certification Form
and be accompanied by the items listed on the |  | Mortgagor's-LIHTC Cost Certification Checklist.
CHFA requires a minimum of 60-days from the date it receives the final Mortgagor’s-LIHTC Cost Certification to issue the Form(s) 8609. The owner/mortgagor must provide adequate and accurate information for the timely issuance of the Form(s) 8609. CHFA reserves the right to return any request(s) for the issuance of Form(s) 8609 if the mortgagor fails to communicate with CHFA regarding delays and concerns.
Adequate records must be maintained by the owner/mortgagor and the general contractor for the purpose of verifying costs. All books, records, contracts, invoices, reports, particulars of material, labor, and equipment entering into the construction (if any) of the development, and other records appropriate to such accounts must be made available to CHFA and its representatives for inspection and copying upon request.
VI. Total Development Costs (TDC)
TDC means the sum total of all costs incurred in the development of a multifamily rental housing, which are approved by as reasonable and necessary, including, but not limited to (1) costs of land acquisition and any buildings thereon; (2) costs of site preparation, demolition and development; (3) architectural, engineering, legal, CHFA and other fees and charges paid or payable in connection with the planning, execution and financing of the project; (4) cost of necessary studies, surveys, plans and permits; (5) insurance, interest, financing, tax and assessment costs and other operating and carrying costs during construction; (6) cost of construction or reconstruction, and fixtures and equipment related to such construction or reconstruction; (7) cost of land improvements; (8) necessary expenses in connection with the initial occupancy of the project; (9) a reasonable profit or fee to the builder and developer; (10) an allowance established by CHFA for working capital, replacement and contingency reserves, and reserves for any anticipated operating deficits during the first two years of occupancy; (11) the cost of such other items, including tenant relocation, as CHFA shall deem to be reasonable and necessary for the development of the project, less any and all net rents and other net revenues received from the operation of the real and personal property on the project site during construction;
The TDC may also include costs approved by CHFA as appropriate expenditures which may be incurred prior to initial disbursement of mortgage loan proceeds, including, but not limited to: (1) Payments for options to purchase properties for the proposed project, deposits on contracts of purchase or, with the prior approval of CHFA, payments for the purchase of such properties; (2) legal, organizational and marketing expenses, including payment of attorneys' and consultants' fees, project management and clerical staff salaries, office rent and other incidental expenses; (3) payment of fees for preliminary feasibility studies and advances for planning, architectural and engineering work and land surveys and soil tests; (4) expenses of surveys as to need and market analyses; (5) necessary application and other fees to federal, state and local government agencies; and (6) such other expenses as may deem appropriate, at the sole discretion of CHFA.
However, not all costs included in the TDC are necessarily recognizable in determining the eligible basis and the amount of LIHTCs to be allocated. Eligible costs for all LIHTC-funded developments are outlined in the Code. It is generally equal to the adjusted basis of the building, including amenities and common areas but excluding land.
VI. Treatment of Assets/Costs for IRC §42 Purposes
The following is a list of the types of costs for LIHTC developments and how the costs should be treated for IRC §42 purposes. The list is not exclusive. The costs are categorized as follows:
§ Assets/Costs Associated with LIHTC Buildings
§ Assets/Costs Associated with Land
§ Costs Associated with Land Improvements
§ Financing Costs
§ Costs Excluded from Eligible Basis
§ Miscellaneous
Assets/Costs Associated with LIHTC Buildings
Developer Fees - Developer fees are paid for services provided to develop the development from its initial inception to its completion when the development is placed in service. Only the portion of the developer fee paid/accrued for providing services associated with the LIHTC buildings is includable in eligible basis.
Consulting Fees - Fees paid to consultants for development-related services may be included in eligible basis if the service is associated with the LIHTC building.
Accounting Costs - Costs incurred during the construction period to account for the costs of construction are indirect costs that directly benefit, or are incurred by reason of, the development owner's improvement and, therefore, are capitalized to the basis of the property improved under IRC §§ 263(a) and 263A. The accounting costs should be allocated among the property improved, and to the extent the cost of the improved property is includible in eligible basis, the improved property's allocated share of the accounting costs are also includible in eligible basis. Accounting costs include, for example, accounting for costs according to the construction contract, securing advances from a construction loan or submitting documentation to HUD for reimbursement.
Land Preparation - The grading of land involves moving soil for the purpose of changing the ground surface. It produces a more level surface and generally provides an improvement that adds value to the land. However, costs attributable to grading land that is done to provide a proper setting for a building become a part of the cost basis of the building.
Excavating, Backfilling, Removal Costs - Earth-moving costs incurred for digging spaces and trenches for a building's foundation and utilities are generally considered to be inextricably associated with the building, are added to the cost of the building and, therefore, are depreciable. Similarly, costs incurred for fill dirt used to set the foundation of a depreciable asset are generally considered to be inextricably associated with the depreciable asset and are depreciable. Rev. Rul. 65-265, as clarified by Rev. Rul. 68-193, holds that excavating, grading, and removal costs directly associated with the construction of buildings and paved roadways are not inextricable associated with the land and should be included in the depreciable basis of the buildings and roadways.
Utilities Tap Fee - Fees paid to a local government for the right to tap into an existing local utility are usually building-specific and capitalized to the building.
Impact Fees - Rev. Rul. 2002-9 provides guidance for including impact fees for determining the eligible basis. Impact fees are assessed because of the development owner's plans to construct a new residential building. Impact fees are indirect costs under IRC §263A because they directly benefit, and are incurred by reason of, the construction of the development. Under Treas. Reg. 1.263A-1(e)(3)(i), the development owner must allocate the impact fees to the property produced. Because impact fees are calculated based upon the characteristics of the building and the impact fees are generally refundable if the building is not constructed as planned, the fees are 100% allocable to the building.
Dedicated Improvements - Similar to the treatment of impact fees, costs to construct dedicated infrastructure improvements are indirect costs under IRC §263A because they directly benefit, or are incurred by reason of, the construction of the development. Infrastructure improvements include, for example, streets, curbs, sidewalks, and storm water drainage required by the local government and constructed according to the local government's specifications. To qualify, the improvements must be dedicated to the state or local government for public use after completion. Upon acceptance of the dedication, the state or local government will own and maintain the infrastructure assets. Treas. Reg. §1.263(a)-4(d)(8)(iv). See PLR 200916007. Under Treas. Reg. §1.263A-1(e)(3)(i), the development owner must allocate the costs to the property produced. If the development encompasses multiple buildings, the costs must be allocated among the buildings constructed using a reasonable method of allocation under Treas. Reg. §1.263A-1(f). See PLR 200916007
Personal Property - Fixtures, Furniture, Appliances - Personal property (e.g., fixtures, furniture and appliances) may be included in eligible basis. Treas. Reg. §1.103-8(b)(4)(iii).
Assets/Costs Associated with Land
Expenses related to acquiring the land are excluded from eligible basis. These costs are capitalized under IRC§§ 1016 and 263. Generally, land acquisition involves the purchase of unimproved land for the construction of IRC §42 developments. Activities normally performed by a developer and associated with the acquisition of land, which should be capitalized to the land, include (but are not limited to):
§ Analysis of the Qualified Allocation Plan (QAP) for targeted areas within a state;
§ Identification of potential land sites;
§ Analysis of population demographics for potential sites;
§ Analysis of a site's economy and forecast future growth potential;
§ Determining a site's zoning status and possible rezoning actions;
§ Contacting local government regarding access to utilities, impact fees and local ordinances, etc.
§ Performing environmental tests on selected sites; and
§ Negotiating the purchase of the land and its related financing.
The above list is not meant to be comprehensive and each activity may have underlying tasks.
Finder’s fees and brokerage fees paid for assistance in acquiring title to a property are also included in land basis and excluded from eligible basis.
Legal and professional fees related to the acquisition of land are also included in land basis and excluded from eligible basis.
Land Acquisition - Assumed Liabilities - Unpaid real estate taxes and similarly assumed costs are added to the land's basis.
Demolition & Tenant Relocation - IRC §280B states that in the case of the demolition of any structure, no deduction is allowed to the owner or lessee of such structure for any amount expended for the demolition, or any loss sustained on account of the demolition. The costs should be added to the capital account for the land on which the demolished structure was located. Therefore, these costs are excluded from eligible basis.
The costs of relocating tenants out of an acquired building that will be demolished may be associated with the demolition and, if so, are capitalized to the land.
Land Preparation Costs - Clearing, Grubbing, Cutting, Filling, Rough Grading - Rev. Rul. 80-93 addresses whether a development owner is allowed to take a depreciation deduction for costs incurred for the clearing, grubbing, cutting, filling and rough and finish grading necessary to bring the land to a suitable grade for constructing certain depreciable assets. These costs will not be repeated when the depreciable asset is replaced. This revenue ruling holds that the land preparation costs are unaffected by replacement of the depreciable assets and will not be replaced contemporaneously. Therefore, they are nonrecurring general land improvement costs that are inextricably associated with the land and are to be added to the development owner's cost basis in the land. These land preparation costs are not depreciable and, therefore, are excluded from eligible basis.
Land Preparation Costs - Grading - The grading of land involves moving soil for the purpose of changing the ground surface. It produces a more level surface and generally provides an improvement that adds value to the land. Rev. Rul. 65-265, clarified by Rev. Rul. 68-193, holds that such expenditures are inextricably associated with the land and, therefore, fall within the rule that land is a non-depreciable asset. Costs attributable to the general grading of the land (not done to provide a proper setting for a building or a paved roadway) become a part of the cost basis of the land and, therefore, are not subject to a depreciation allowance.
Land Surveys - Boundary, Mortgage - Land and environmental surveys are generally conducted over the entire property of the development, not just where the buildings and improvements will be specifically placed. Some surveys, such as boundary or mortgage surveys help to define the property. Costs incurred for these types of survey are inextricably associated with the land, are not depreciable, and are excluded from eligible basis. See TAM 200043017.
Environmental Surveys - Percolation Tests, Contamination Studies, Soil Borings, Geotechnical Inspections, Wetland Studies, Groundwater Investigations - Environment surveys such as percolation tests and contamination studies are used to determine if the land is suitable for the construction of the contemplated improvements. Other similar surveys include soil borings, geotechnical investigations, suitability studies, wetland reviews, mapping of wetland, and inspections of wetland, wetland characterization, and groundwater investigations. If this type of survey will not necessarily need to be redone contemporaneously when the depreciable improvement is replaced, the costs incurred for the survey are inextricably associated with the land and are not depreciable and are excluded from eligible basis. A survey is considered to be redone contemporaneously with the replacement of the depreciable improvement if the physical replacement of the depreciable improvement (which is included in eligible basis) mandates a re-performance of the survey. Although an ordinance may require re-performance of the survey, such requirement is irrelevant as to whether the physical replacement of a depreciable improvement necessarily mandates a re-performance of the survey.
If necessary, the cost should be allocated between non-depreciable property (for example, land) and depreciable property (for example, buildings) using any reasonable method. For example, if staking costs are incurred to demarcate sidewalks (depreciable) and landscaping not immediately adjacent to buildings (non-depreciable), the staking costs should be allocated between the sidewalks and the landscaping. See TAM 200043017
Costs Associated with Land Improvements
Generally, land preparation and improvement costs are excluded from eligible basis. For a land cost to be included in eligible basis, it must be so closely associated with a particular depreciable asset includable in eligible basis that the land improvement will be retired, abandoned, or replaced contemporaneously with that depreciable asset; i.e., the cost will be re-incurred if the depreciable asset is replaced or rebuilt. Whether a specific land cost will be retired, abandoned, or replaced contemporaneously with the depreciable asset is a question of fact.
Landscaping - Clearing, General Grading, Top soil, Seeding, Finish Grading, Planting of Perennial Shrubbery and Trees - Landscaping immediately adjacent to a LIHTC building is depreciable property if the replacement of the building will destroy the landscaping. In such a case, these costs are considered inextricably associated with the building and, therefore, are a depreciable land improvement. These costs are included in eligible basis. Otherwise, landscaping that will be unaffected by the replacement of the building and, therefore, will not be replaced contemporaneously, is a non-depreciable land improvement. These costs are excluded from eligible basis. See Rev. Rul. 74-265.
Engineering and Architectural Services - Engineering and architectural services may include (but are not limited to) the preparation of erosion control plan, grading plan, utility plans, general details, easement descriptions, sewer and sanitary plans, and traffic engineering. Such services associated with non-depreciable land are excluded from eligible basis.
The services associated with a tangible depreciable asset includable in eligible basis, such as detailed construction drawings, are includable in eligible basis.
While it is a case-by-case factual determination, engineering and architectural services should be characterized consistently with the subject of the service. Services that may be associated with both non-depreciable property (e.g., land) and depreciable property should be allocated among the non-depreciable property and the depreciable property using a reasonable method.
Financing Costs
Fee, Cash Flow Guarantee - A "cash flow guarantee fee" paid by a partnership to secure agreement that its general partner would make loans to the partnership to fund any operating deficits is excluded from eligible basis.
Fee, Tax Credit Guarantee - A "tax credit guarantee fee" paid to ensure that the development is operated in compliance with IRC §42 and guarantee that the development owner is entitled to claim the IRC §42 credit is excluded from eligible basis.
Tax-Exempt Bonds - Issuance Costs - Notwithstanding the general rule of IRC §263A, bond issuance costs are excluded from eligible basis under the specific requirements of IRC §42(d)(1). See TAM 200043015.
Loans - Origination Fees, Legal Fees, Closing Costs, Title Searches, Recordation Fees - Costs incurred in obtaining a loan are capitalized and amortized over the life of the loan. The cost of securing financing includes costs such as origination fees, legal fees, closing costs, title searches and recordation fees.
Construction Loans - The costs and fees incurred in obtaining a construction loan are not capitalized to depreciable property, but are treated as an amortizable IRC §167 intangible. The costs for obtaining a construction loan relate to the land acquired as well as the land improvements, in addition to the buildings. IRC §263A requires the amortization deductions relating to the construction loan be capitalized to the produced property during the construction period. The deductions must be reasonably allocated to all property produced. See TAM 200044005.
Permanent Financing - The cost of securing permanent financing is excluded from eligible basis, but to the extent the loan is associated with the building, capitalization of the amortization during the construction period may be required under IRC §263A. However, permanent financing is not usually in place during the construction period. Bridge loans are treated the same way.
Loans: Reserves and Escrows Required by Lender - Funds held in escrow accounts or required by a lender to be held in reserve are not depreciated and are excluded from eligible basis.
Loans: Interest Paid or Incurred - Interest paid or incurred during the "production" period of a LIHTC building that is allocable to the production expenditures of the building is capitalized to the building under IRC §263A(f) and includable in eligible basis. Generally, the production period begins when physical activity on the site begins and ends when the produced property is placed in service. Physical production excludes planning and architectural design, soil testing, or securing permits. Treas. Reg. §1.263A-12(f). The determination of whether interest is allocable to the production of the building is made using the "avoided cost" method. See Treas. Reg. §1.263A-8(a).
Interest attributable to a completed LIHTC building that is paid or incurred after the production period for the building for purposes of IRC §263A(f) has ended, is expensed as an ordinary and necessary business expense.
If dwelling units within a LIHTC building are separately placed in service, interest attributable to these dwelling units that is paid or incurred after the production period for the dwelling units for purposes of IRC §263A(f) has ended, is expensed as an ordinary and necessary business expense. However, if the dwelling units are separately placed in service before the development of the LIHTC building or construction of the improvement to the LIHTC building has been completed for purposes of IRC §266, a development owner may elect under IRC §266 and Treas. Reg. §1.266-1(b)(1)(ii) to capitalize to the building the interest attributable to these dwelling units that is incurred after the production period for the dwelling units for purposes of IRC §263A(f) has ended but before the development of the LIHTC building or construction of the improvement to the LIHTC building has been completed for purposes of IRC §266. See Treas. Reg. §1.266-(1)(a)(2).
Costs Excluded from Eligible Basis
IRC §42 Credit Application & Allocation Fees
IRC §42 Credit: Cost Certifications - The cost of preparing the cost certifications is excluded from eligible basis because this cost is incurred to secure an allocation of the IRC §42 credit and, therefore, is not capitalized to the basis of the building under IRC §263(a) or IRC §263A.
Compliance Monitoring Fees - These fees are ordinary and necessary business expense under IRC §162 in the year the fee is incurred or paid. The cost is not depreciable and, therefore, is excluded from eligible basis.
Management Fee - "Rental management" is the continuing day-to-day management of the property, including all dealings with the tenants, leasing and renewal of current leases, procurement of new tenants for any vacancies, etc. Rental management fees are usually a set amount plus a percentage for any lease renewals and incentives for new tenants obtained to fill vacancies. Amounts paid for the original leasing of the units and continued management of the development should be expensed on a yearly basis and matched against current rental income. These fees are excluded from eligible basis.
Partnership Organizational Costs - The cost of organizing a partnership may be amortized over a period of time not less than 60 months under IRC §709(b). These costs are not included in adjusted basis for depreciation purposes and are, therefore, excluded from eligible basis.
Treas. Reg. §1.709-2(a) defines "organizational expenses" as expenses that are: (1) incident to the creation of the partnership; (2) chargeable to capital account; and (3) of a character that, if expended incident to the creation of a partnership having an ascertainable life, would (but for IRC §709(a)) be amortized over that life. An expenditure that fails to meet one or more of the three tests does not qualify as an organizational expense for purposes of IRC §709(b) and Treas. Reg. §1.709-2(a).
Examples of organizational expenses include legal fees for services incident to the organization of the partnership, such as negotiation and preparation of a partnership agreement; accounting fees for services incident to the organization of the partnership; and filing fees. Examples of expenses that are not organizational expenses include costs to acquire assets for the partnership or transferring assets to the partnership; expenses connected with the admission or removal of partners other than at the time the partnership is first organized; expenses connected with a contract relating to the operation of the partnership trade or business (even where the contract is between the partnership and one of its members); and syndication expenses. See TAM 200043017.
Partnership Syndication Costs - Treas. Reg. §1.709-2(b) defines "syndication expenses" as expenses connected with the issuing and marketing of interests in the partnership. Examples of syndication expenses are brokerage fees; registration fees; legal fees of the underwriter or placement agent and the issuer (the general partner or the partnership) for securities advice and for advice pertaining to the adequacy of tax disclosures in the prospectus or placement memorandum for securities law purposes; accounting fees for preparation of representations to be included in the offering materials; and printing costs of the prospectus, placement memorandum, and other selling and promotional material.
These expenses are not subject to the election under IRC §709(b) and must be capitalized, and are not includable in adjusted basis for depreciation purposes. Therefore, partnership syndication costs are excluded from eligible basis. Rev. Rul. 85-32 explains that syndication costs incurred in connection with the sale of limited partnership interests are chargeable by the partnership to a capital account and cannot be amortized. See TAM 200043017.
Cost Incurred to Permanently Relocate Non-qualifying Tenants - The costs attributable to moving out the tenant permanently (e.g.; legal costs, tenant moving expenses, and compensation paid to the tenant) are expensed as an ordinary and necessary business expense under IRC §162, even if the vacated unit is rehabilitated.
Costs Incurred to Temporarily Relocate Qualifying Tenants During the Rehabilitation - A determination may be made that an existing tenant is a qualified low-income household. In which case, the development owner will move the tenant and provide temporary housing while the tenant's unit is being rehabilitated. The temporary housing may be another unit within the development or off-site. The tenant is expected to occupy the rehabilitated unit after the rehabilitation is completed. The costs attributable to moving the tenant and providing temporary housing for the tenant during the rehabilitation (e.g.; legal costs, tenant moving expenses, costs for temporarily storing a tenant's property, and temporary housing costs) are expensed as ordinary and necessary business expenses under IRC §162.
"Rent-Up" Marketing and Advertising Costs - "Rent up" or "lease up" costs are the costs necessary to initially rent out a newly placed in service LIHTC building or development. Costs may include advertising, maintaining a model unit, providing housing for on-site rental managers and staff, and any other costs to fully rent out the buildings. Rent-up costs are not related to the construction of the buildings, but for securing tenants. These costs do not establish or add to the basis of depreciable property and are excluded from eligible basis. See TAM 200043017.
Miscellaneous Costs
Real Estate Taxes: Assumed Liability - Delinquent real estate taxes assumed at acquisition are included in the basis of the land. Therefore, the cost of delinquent real estate taxes assumed at acquisition is excluded from eligible basis.
Real Estate Taxes: Incurred During Pre-Production Period - When real property is acquired with the intent to develop it, real estate taxes paid are required to be capitalized under IRC §263A, even if no positive steps to begin developing the property has occurred.
Real Estate Taxes: Incurred During Construction Period - Real estate taxes incurred during the construction period and capitalizable to the LIHTC buildings under IRC §263A are included in eligible basis.
Real Estate Taxes: Incurred After Buildings are Placed in Service - Real estate taxes incurred after the buildings are placed in service are expensed as ordinary and necessary business expenses and are excluded from eligible basis.
Carrying Charges Other Than Interest - IRC §266 permits development owners to elect to capitalize certain otherwise deductible carrying charges paid or incurred with respect to improved but unproductive real property. A LIHTC building that has been placed in service may contain vacant units that have been rehabilitated and are available for rent but have not yet been rented out. A development owner may pay or incur payroll and utility costs attributable to those vacant units during the first year of the credit period. Under Rev. Rul. 71-475, 1971-2 C.B. 304, advertising expenses attributable to unproductive property, and maintenance and upkeep costs attributable to improved and unproductive real property, are not carrying charges chargeable to a capital account under IRC §266. Thus, payroll and utility costs attributable to those vacant units are not carrying charges for purposes of IRC §266.
However, carrying charges (other than interest) that are attributable to vacant units that have been rehabilitated for which the production period for purposes of IRC S263A(f) has ended, that are available for rent but have not yet been rented out, and are located in a LIHTC building that has been placed in service are capitalized to the building under IRC §263A as post-production costs. See Treas. Reg. §1.263A-2(a)(3)(iii).

## G.C. Cost Cert Checklist
Version 2020.1
General Contractor's Cost Certification Submittal Checklist
Please read the |  | CHFA Cost Certification Preparation Guideline | prior to preparing the
General Contractor's Certificate of Actual Cost
The following documents must be submitted with the General Contractor’s Cost Certification:
1 | Color copy of the most recent signed and approved Project Cost Summary (signed by both GC and Mortgagor);
2 | Copy of the fully-executed General Contractor’s contract;
3 | Excel workbook for the General Contractor’s Cost Certification completed by the CPA(s); It must include schedules to support costs for Base Project (Divisions 2-16), General Requirements and Change Orders.
4 | Draft pdf copy of General Contractor’s Cost Certification completed by the CPA(s). CPA(s): Do not finalize the General Contractor’s Cost Certification until CHFA review is finalized;
5 | Once the General Contractor’s Cost Certification review is finalized, provide one (1) original bound copy of the General Contractor’s Cost Certification signed by the general contractor/construction manager and the signature executed in blue ink must be notarized for CHFA record. The certifications must be accompanied by an Independent Auditor’s Report, including the unqualified opinion of the CPA; and,
6 | Color PDF copy of the executed notarized General Contractor’s Cost Certification.
7 | Developments not financed through CHFA may be required to submit copies of approved general contractor’s change orders and owner's change orders at CHFA's discretion
8 | Developments not financed through CHFA may be required to submit copies of invoice(s) of check(s) for the building permit(s) and bond premiums at CHFA's discretion

## Gen.Contr. Cert. of Actual Cost
Version 2020.1
CHFA Cost Certification Preparation Guideline
GENERAL CONTRACTOR'S CERTIFICATE OF ACTUAL COST
Owner Name:
Owner Mailing Address:
Development Name:
Development Address:
CHFA Development Number: | [6 empty] | LIHTC Number:
Preparing CPA Firm Name and Address:
CPA's Phone Number: | [6 empty] | CPA's E-mail Address:
To: | Connecticut Housing Finance Authority (CHFA) | [5 empty] | General Contractor:
To Whom It May Concern:
This Certificate is made pursuant to the provisions of the Construction Contract, entered into by and between Owner's Name and General Contractor's Name on date and it is understood and agreed by the undersigned that this Certificate is to be submitted by you to CHFA in order to induce CHFA to proceed to final closing.
The actual cost incurred in the completion of construction under the above Construction Contract and accepted construction changes exclusive of all kickbacks, rebates and discounts received in connection with the construction of the project is itemized below.
LINE | DIV. | DIVISION / TRADE ITEM |  | PAID IN CASH | PAID IN CASH |  | TO BE PAID IN CASH | TOTAL | NAME OF SUBCONTRACTOR OR PAYEE
1 | 2 | Testing |  |  | 0 |  | 0 | 0
2 | 2 | Environmental |  |  | 0 |  | 0 | 0
3 | 2 | Grading & Excavation |  |  | 0 |  | 0 | 0
4 | 2 | Site Utilities |  |  | 0 |  | 0 | 0
5 | 2 | Paving, Walks & Signs |  |  | 0 |  | 0 | 0
6 | 2 | Unusual Site Conditions |  |  | 0 |  | 0 | 0
7 | 2 | Lawns & Plantings |  |  | 0 |  | 0 | 0
8 | 2 | Other Site Work |  |  | 0 |  | 0 | 0
9 | 2 | Demolition |  |  | 0 |  | 0 | 0
10 | 2 | Allowance for Division 2 |  |  | 0 |  | 0 | 0
11 | 3 | Concrete |  |  | 0 |  | 0 | 0
12 | 3 | Allowance for Division 3 |  |  | 0 |  | 0 | 0
13 | 4 | Masonry |  |  | 0 |  | 0 | 0
14 | 4 | Allowance for Division 4 |  |  | 0 |  | 0 | 0
15 | 5 | Metals |  |  | 0 |  | 0 | 0
16 | 5 | Allowance for Division 5 |  |  | 0 |  | 0 | 0
17 | 6 | Rough Carpentry |  |  | 0 |  | 0 | 0
18 | 6 | Finish Carpentry |  |  | 0 |  | 0 | 0
19 | 6 | Allowance for Division 6 |  |  | 0 |  | 0 | 0
20 | 7 | Moisture Protection |  |  | 0 |  | 0 | 0
21 | 7 | Insulation |  |  | 0 |  | 0 | 0
22 | 7 | Roofing |  |  | 0 |  | 0 | 0
23 | 7 | Sheet Metal |  |  | 0 |  | 0 | 0
24 | 7 | Siding |  |  | 0 |  | 0 | 0
25 | 7 | Allowance for Division 7 |  |  | 0 |  | 0 | 0
26 | 8 | Doors & Hardware |  | 19515 | 0 |  | 0 | 0
27 | 8 | Windows & Glazing |  | 20665 | 0 |  | 0 | 0
28 | 8 | Allowance for Division 8 |  | 53406 | 0 |  | 0 | 0
29 | 9 | Acoustical Tile |  |  | 0 |  | 0 | 0
30 | 9 | Drywall |  |  | 0 |  | 0 | 0
31 | 9 | Ceramic Tile |  |  | 0 |  | 0 | 0
32 | 9 | Wood Flooring |  |  | 0 |  | 0 | 0
33 | 9 | Resilient Flooring |  | 24898.34 | 0 |  | 0 | 0
34 | 9 | Painting and Decorating |  | 13000 | 0 |  | 0 | 0
35 | 9 | Carpet |  |  | 0 |  | 0 | 0
36 | 9 | Allowance for Division 9 |  |  | 0 |  | 0 | 0
37 | 10 | Unit AC and/or Sleeves |  | 750 | 0 |  | 0 | 0
38 | 10 | Specialties |  | 79170.5 | 0 |  | 0 | 0
39 | 10 | Allowance for Division 10 |  |  | 0 |  | 0 | 0
40 | 11 | Special Equipment (Specify) |  |  | 0 |  | 0 | 0
41 | 11 | Cabinets & Vanities |  |  | 0 |  | 0 | 0
42 | 11 | Appliances |  |  | 0 |  | 0 | 0
43 | 11 | Allowance for Division 11 |  |  | 0 |  | 0 | 0
44 | 12 | Blinds, Shades & Artwork |  |  | 0 |  | 0 | 0
45 | 12 | Allowance for Division 12 |  |  | 0 |  | 0 | 0
46 | 13 | Special Construction |  |  | 0 |  | 0 | 0
47 | 13 | Allowance for Division 13 |  |  | 0 |  | 0 | 0
48 | 14 | Elevators |  |  | 0 |  | 0 | 0
49 | 14 | Allowance for Division 14 |  |  | 0 |  | 0 | 0
50 | 15 | Plumbing |  |  | 0 |  | 0 | 0
51 | 15 | Hydronic Heating |  |  | 0 |  | 0 | 0
52 | 15 | HVAC |  |  | 0 |  | 0 | 0
53 | 15 | Fire Suppression |  |  | 0 |  | 0 | 0
54 | 15 | Allowance for Division 15 |  |  | 0 |  | 0 | 0
55 | 16 | Electrical (Building Only) |  |  | 0 |  | 0 | 0
56 | 16 | Allowance for Division 16 |  | 12500 | 0 |  | 0 | 0
57 |  | SUBTOTAL (DIVISION 2-16) |  |  | 0 |  | 0 | 0
58 |  | General Requirements |  | 17382.89 | 0 |  | 0 | 0
59 |  | SUBTOTAL (LINES 57 & 58) |  | 5997.09 | 0 |  | 0 | 0
60 |  | Builder's Overhead & Profit |  |  | 0 |  | 0 | 0
61 |  | SUBTOTAL (LINES 59 & 60) |  |  | 0 |  | 0 | 0
62 |  | Building Permit & Other Fees |  |  | 0 |  | 0 | 0
63 |  | Bond Premium |  |  | 0 |  | 0 | 0
64 |  | TOTAL FOR ALL IMPROVEMENTS |  |  | 0 |  | 0 | 0
65 |  | CHFA Approved Change Orders |  |  | 0 |  | 0 | 0
66 |  | PROJECT SUMMARY TOTAL |  | 318281 | 0 | 0 | 0 | 0
Note: | If additional space is required for these or other items, append rider thereto, with references and initial. When more than one Subcontractor is performing a trade item, the attached worksheet must be completed giving the information indicated.
ITEMIZED BREAKDOWN
GENERAL REQUIREMENTS
( Project Overhead) | [8 empty] | OTHER FEES
|  | ITEM | TOTAL |  |  |  |  | ITEM |  | TOTAL
Supervision |  |  | 0 | $
Field Engineering |  |  | 0
Field Office Expense |  |  | 0 |  |  | $
Temporary Facilities | [5 empty] | $
Temporary Utilities |  |  | 0 |  |  | $
Cleaning & Rubbish Removal |  |  | 0
Watchmen Wages (Security) |  |  | 0 |  |  | $
|  |  | 0 | $
|  |  | 0 | $
0
TOTAL FOR
GENERAL REQUIREMENTS |  |  | 0 | [5 empty] | TOTAL | $
To be paid in cash
within 45 days after
|  |  | Paid in Cash |  |  |  | final endorsement |  |  | Total
Miscellaneous Materials & Labor |  |  | $ |  |  |  | $ |  |  | $
(Not included in Contracts)
* Total purchases of materials and cost of labor amounting to less than $1,000.00 may be included as a lump sum under
miscellaneous materials and labor. Costs exceeding this amount for materials and labor must be allocated to the trade item
under which they were expended on CHFA Project Cost Summary and Cost Certification worksheets A, B and C.
Note: |  | Total costs for General Requirements, other Fees, Miscellaneous Materials and Miscellaneous labor are to be
transferred to the appropriate line item on the reverse side.
All amounts shown have been reduced to give effect to the amount(s) of any kickbacks, rebates, adjustments, discounts or any
other devices which had the effect of reducing the actual cost, and all amounts above as "To Be Paid In Cash" will be so paid
within 45 days after Final Closing.
Signature of General Contractor |  |  |  |  | Name/Title: |  |  |  | Date:
Duly Authorized
STATE OF__________________________
COUNTY OF________________________ |  |  |  |  | SS: ________________________________
Notary Public
My commission expires:_______________________

## G.C.Cost Data Sheet-Stip Sum (hidden)
Version 2020.1
GENERAL CONTRACTOR'S COST DATA SHEET
CONNECTICUT HOUSING FINANCE AUTHORITY
|  |  | Development Name: | 0
|  |  | Development Address: | 0
|  |  | CHFA Development #: | 0
|  |  | LIHTC #: | 0 |  | Type of G. C. Contract: Stipulated Sum
A | B | C | D | E | F | G | H
LINE | DIV. | DIVISION | CHFA APPROVED PROJECT COST SUMMARY | CONTRACTOR'S CERTIFICATION AMOUNT | COMMENTS
1 | 2 | Testing | 0 | 0
2 | 2 | Environmental | 0 | 0 |  |  |  | Stipulated Sum
3 | 2 | Grading & Excavation | 0 | 0 |  |  |  | Guaranteed Maximum Price
4 | 2 | Site Utilities | 0 | 0
5 | 2 | Paving, Walks & Signs | 0 | 0
6 | 2 | Unusual Site Conditions | 0 | 0
7 | 2 | Lawns & Plantings | 0 | 0
8 | 2 | Other Site Work | 0 | 0
9 | 2 | Demolition | 0 | 0
10 | 2 | Allowance for Division 2 | 0 | 0
11 | 3 | Concrete | 0 | 0
12 | 3 | Allowance for Division 3 | 0 | 0
13 | 4 | Masonry | 0 | 0
14 | 4 | Allowance for Division 4 | 0 | 0
15 | 5 | Metals | 0 | 0
16 | 5 | Allowance for Division 5 | 0 | 0
17 | 6 | Rough Carpentry | 0 | 0
18 | 6 | Finish Carpentry | 0 | 0
19 | 6 | Allowance for Division 6 | 0 | 0
20 | 7 | Moisture Protection | 0 | 0
21 | 7 | Insulation | 0 | 0
22 | 7 | Roofing | 0 | 0
23 | 7 | Sheet Metal | 0 | 0
24 | 7 | Siding | 0 | 0
25 | 7 | Allowance for Division 7 | 0 | 0
26 | 8 | Doors & Hardware | 0 | 0
27 | 8 | Windows & Glazing | 0 | 0
28 | 8 | Allowance for Division 8 | 0 | 0
29 | 9 | Acoustical Tile | 0 | 0
30 | 9 | Drywall | 0 | 0
31 | 9 | Ceramic Tile | 0 | 0
32 | 9 | Wood Flooring | 0 | 0
33 | 9 | Resilient Flooring | 0 | 0
34 | 9 | Painting and Decorating | 0 | 0
35 | 9 | Carpet | 0 | 0
36 | 9 | Allowance for Division 9 | 0 | 0
37 | 10 | Unit AC and/or Sleeves | 0 | 0
38 | 10 | Specialties | 0 | 0
39 | 10 | Allowance for Division 10 | 0 | 0
40 | 11 | Special Equipment (Specify) | 0 | 0
41 | 11 | Cabinets & Vanities | 0 | 0
42 | 11 | Appliances | 0 | 0
43 | 11 | Allowance for Division 11 | 0 | 0
44 | 12 | Blinds, Shades & Artwork | 0 | 0
45 | 12 | Allowance for Division 12 | 0 | 0
46 | 13 | Special Construction | 0 | 0
47 | 13 | Allowance for Division 13 | 0 | 0
48 | 14 | Elevators | 0 | 0
49 | 14 | Allowance for Division 14 | 0 | 0
50 | 15 | Plumbing | 0 | 0
51 | 15 | Hydronic Heating | 0 | 0
52 | 15 | HVAC | 0 | 0
53 | 15 | Fire Suppression | 0 | 0
54 | 15 | Allowance for Division 15 | 0 | 0 | F | G | H
55 | 16 | Electrical (Building Only) | 0 | 0 | CHFA RECOGNIZED COST | DIFFERENCE | COMMENTS
56 | 16 | Allowance for Division 16 | 0 | 0 |  | (F LESS E)
57 |  | SUBTOTAL (DIVISION 2-16) | 0 | 0 | 0 | 0
58 |  | General Requirements | 0 | 0 | 0 | 0
59 |  | SUBTOTAL (LINES 57 & 58) | 0 | 0 | 0
60 |  | Builder's Overhead & Profit | 0 | 0 | 0 | 0
61 |  | SUBTOTAL (LINES 59 & 60) | 0 | 0 | 0
62 |  | Building Permit & Other Fees | 0 | 0 | 0 | 0
63 |  | Bond Premium | 0 | 0 | 0 | 0
64 |  | TOTAL FOR ALL IMPROVEMENTS | 0 | 0 | 0
65 |  | CHFA Approved Change Orders | 0 | 0 | 0 | 0 |  |  | 0
66 |  | Less CHFA Approved Owner Change Orders |  |  | 0 | 0
67 |  | PROJECT SUMMARY TOTAL | 0 | 0 | 0 | 0
A | B | C | D | E | F | G
|  | TOTAL CHFA APPROVED DISBURSED AMOUNTS |  |  | 0
|  | TOTAL CHFA RECOG. CONST. CONTINGENCY (Net of Owner's Change Orders) |  |  | 0
|  | TOTAL CHFA RECOGNIZED COST |  |  | 0
Note: CHFA Scope for Cost Certification Review is Limited in nature
Completed By: |  |  | Date |  | Approved By: |  | Date
Architect |  |  |  |  | Director - Multifamily
Note on E14: Kabir, Mahjabeen: This column will be automatically populated from the Contractor's Cert of Actual Cost
Note on D79: Kabir, Mahjabeen: Enter the total amount from the Change Order Log in MFaSys.
Note on F79: Kabir, Mahjabeen: Enter from Change Order Request in MFaSys.
Note on F80: Kabir, Mahjabeen: Enter as a negative number from Change Order Request in MFaSys.

## G.C.Cost Data Sheet-GMP (hidden)
Version 2020.1
GENERAL CONTRACTOR'S COST DATA SHEET
CONNECTICUT HOUSING FINANCE AUTHORITY
|  |  | Development Name: | 0
|  |  | Development Address: | 0
|  |  | CHFA Development #: | 0
|  |  | LIHTC #: | 0 | Type of G. C. Contract: Guaranteed Maximum Price
A | B | C | D | E | F | G
LINE | DIV. | DIVISION | CHFA APPROVED PROJECT COST SUMMARY | CONTRACTOR'S CERTIFICATION AMOUNT | CHFA RECOGNIZED COST | DIFFERENCE F LESS D | COMMENTS
1 | 2 | Testing | 0 | 0 | 0 | 0
2 | 2 | Environmental | 0 | 0 | 0 | 0 |  |  | Stipulated Sum
3 | 2 | Grading & Excavation | 0 | 0 | 0 | 0 |  |  | Guaranteed Maximum Price
4 | 2 | Site Utilities | 0 | 0 | 0 | 0
5 | 2 | Paving, Walks & Signs | 0 | 0 | 0 | 0
6 | 2 | Unusual Site Conditions | 0 | 0 | 0 | 0
7 | 2 | Lawns & Plantings | 0 | 0 | 0 | 0
8 | 2 | Other Site Work | 0 | 0 | 0 | 0
9 | 2 | Demolition | 0 | 0 | 0 | 0
10 | 2 | Allowance for Division 2 | 0 | 0 | 0 | 0
11 | 3 | Concrete | 0 | 0 | 0 | 0
12 | 3 | Allowance for Division 3 | 0 | 0 | 0 | 0
13 | 4 | Masonry | 0 | 0 | 0 | 0
14 | 4 | Allowance for Division 4 | 0 | 0 | 0 | 0
15 | 5 | Metals | 0 | 0 | 0 | 0
16 | 5 | Allowance for Division 5 | 0 | 0 | 0 | 0
17 | 6 | Rough Carpentry | 0 | 0 | 0 | 0
18 | 6 | Finish Carpentry | 0 | 0 | 0 | 0
19 | 6 | Allowance for Division 6 | 0 | 0 | 0 | 0
20 | 7 | Moisture Protection | 0 | 0 | 0 | 0
21 | 7 | Insulation | 0 | 0 | 0 | 0
22 | 7 | Roofing | 0 | 0 | 0 | 0
23 | 7 | Sheet Metal | 0 | 0 | 0 | 0
24 | 7 | Siding | 0 | 0 | 0 | 0
25 | 7 | Allowance for Division 7 | 0 | 0 | 0 | 0
26 | 8 | Doors & Hardware | 0 | 0 | 0 | 0
27 | 8 | Windows & Glazing | 0 | 0 | 0 | 0
28 | 8 | Allowance for Division 8 | 0 | 0 | 0 | 0
29 | 9 | Acoustical Tile | 0 | 0 | 0 | 0
30 | 9 | Drywall | 0 | 0 | 0 | 0
31 | 9 | Ceramic Tile | 0 | 0 | 0 | 0
32 | 9 | Wood Flooring | 0 | 0 | 0 | 0
33 | 9 | Resilient Flooring | 0 | 0 | 0 | 0
34 | 9 | Painting and Decorating | 0 | 0 | 0 | 0
35 | 9 | Carpet | 0 | 0 | 0 | 0
36 | 9 | Allowance for Division 9 | 0 | 0 | 0 | 0
37 | 10 | Unit AC and/or Sleeves | 0 | 0 | 0 | 0
38 | 10 | Specialties | 0 | 0 | 0 | 0
39 | 10 | Allowance for Division 10 | 0 | 0 | 0 | 0
40 | 11 | Special Equipment (Specify) | 0 | 0 | 0 | 0
41 | 11 | Cabinets & Vanities | 0 | 0 | 0 | 0
42 | 11 | Appliances | 0 | 0 | 0 | 0
43 | 11 | Allowance for Division 11 | 0 | 0 | 0 | 0
44 | 12 | Blinds, Shades & Artwork | 0 | 0 | 0 | 0
45 | 12 | Allowance for Division 12 | 0 | 0 | 0 | 0
46 | 13 | Special Construction | 0 | 0 | 0 | 0
47 | 13 | Allowance for Division 13 | 0 | 0 | 0 | 0
48 | 14 | Elevators | 0 | 0 | 0 | 0
49 | 14 | Allowance for Division 14 | 0 | 0 | 0 | 0
50 | 15 | Plumbing | 0 | 0 | 0 | 0
51 | 15 | Hydronic Heating | 0 | 0 | 0 | 0
52 | 15 | HVAC | 0 | 0 | 0 | 0
53 | 15 | Fire Suppression | 0 | 0 | 0 | 0
54 | 15 | Allowance for Division 15 | 0 | 0 | 0 | 0
55 | 16 | Electrical (Building Only) | 0 | 0 | 0 | 0
56 | 16 | Allowance for Division 16 | 0 | 0 | 0 | 0 | GENERAL REQ. AND OH&P TEST
57 |  | SUBTOTAL (DIVISION 2-16) | 0 | 0 | 0
58 |  | Credit Change Orders/Buyout Savings (If applicable) |  |  |  |  | Orig. 2-16 | 0
59 |  | General Requirements | 0 | 0 | #DIV/0! | #DIV/0! | Orig. G.R. | 0
60 |  | SUBTOTAL (LINES 57 & 58) | 0 | 0 | #DIV/0! | #DIV/0! | G.R % | #DIV/0!
61 |  | Builder's Overhead & Profit | 0 | 0 | #DIV/0! | #DIV/0! | Orig. OH&P | 0
62 |  | SUBTOTAL (LINES 59 & 60) | 0 | 0 | #DIV/0! | #DIV/0! | OH&P % | #DIV/0!
63 |  | Building Permit & Other Fees | 0 | 0 | 0 | 0
64 |  | Bond Premium | 0 | 0 | 0 | 0 | CHFA RECOGNIZED G.R AND OH&P
65 |  | TOTAL FOR ALL IMPROVEMENTS | 0 | 0 | #DIV/0! | #DIV/0!
66 |  | CHFA Approved Change Orders |  | 0 | 0 | 0 | Recognized 2-16 | 0 |  | 0
67 |  | Less CHFA Approved Owner Change Orders | 0 |  | 0 | 0 | G.R | #DIV/0!
68 |  | PROJECT SUMMARY TOTAL | 0 | 0 | #DIV/0! | #DIV/0! | OH&P | #DIV/0!
A | B | C | D | E | F | G
|  | TOTAL CHFA APPROVED DISBURSED AMOUNTS |  |  | #DIV/0!
|  | TOTAL CHFA RECOG. CONST. CONTINGENCY (Net of Owner's Change Orders) |  |  | 0
|  | TOTAL CHFA RECOGNIZED COST |  |  | #DIV/0!
Note: CHFA Scope for Cost Certification Review is Limited in nature
Completed By: |  |  | Date |  | Approved By: |  | Date
Architect |  |  |  |  | Director - Multifamily
Note on E14: Kabir, Mahjabeen: This column will be automatically populated from the Contractor's Cert of Actual Cost
Note on D80: Kabir, Mahjabeen: Enter the total amount from the Change Order Log in MFaSys.
Note on F80: Kabir, Mahjabeen: Enter from Change Order Request in MFaSys.
Note on F81: Kabir, Mahjabeen: Enter as a negative number from Change Order Request in MFaSys.

## Mort.-LIHTCCost Cert Checklist
Version 2020.1
Mort.-LIHTC Cost Certification Submittal Checklist
Please read the |  | CHFA Cost Certification Preparation Guideline | prior to preparing the
Mortgagor's-LIHTC Cost Certification.
The development owner should provide the preparing CPA with a copy of the CHFA approved G.C. Cost Data Sheet for the preparation of the Mortgagor's-LIHTC cost certification. CHFA will recognize the CHFA recognized hard cost amounts on the G.C. Cost Data Sheet.
The following documents must be submitted with the Mortgagor's-LIHTC Cost Certification:
1 | One original hard copy of the signed and notarized Mortgagor's-LIHTC Cost Certification. The signature page is included in the Mortgagor's-LIHTC Cost Certification worksheet in this Excel workbook.
2 | Color PDF version, via e-mail, of the executed notarized Mortgagor's-LIHTC Cost Certification.
3 | Excel file for the Mortgagor's-LIHTC Cost Certification Workbook along with the following signed certifications:
| a) | Mortgagor’s Certification of Placed-In-Service Date form for each building
| b) | Letter from the owner requesting the Form(s) 8609 from CHFA
| c) | Syndicator's/Investor's Certification
4 | Independent Auditor’s Report.
5 | Copy of all executed mortgage notes (not the actual mortgages) for all of the loans to the development, including the bridge loan, if applicable, and the permanent loan(s). The owner/mortgagor must provide evidence of funding commitments for any non-debt source(s) of funds
6 | If construction period Net Operating Income (NOI) is a funding source, the CPA must prepare and provide an Operating (or Income and Expense) Statement covering the period from first occupancy to the date of substantial completion to evidence the availability of NOI. If NOI is identified as an original or alternative source of funds, it must be reflected on the cost certification prepared by the CPA.
7 | PDF version, via e-mail, of fully executed Limited Partnership Agreement with the investor limited partner, including all exhibits.

## Mortgagor's-LIHTC Cost Cert.
Version 2020.1
CHFA Cost Certification Preparation Guideline | [11 empty] | II. CERTIFICATION OF COSTS (CONT.) | [6 empty] | III. CALCULATING THE ELIGIBLE BASIS |  |  |  | IV. CALCULATING THE APPLICABLE FRACTION |  |  | SOURCES OF FUNDS: | [5 empty] | Addendum to Mortgagor's LIHTC Cost Certification
CONNECTICUT HOUSING FINANCE AUTHORITY | [6 empty] | II. CERTIFICATION OF COSTS |  | Eligible Basis |  |  |  |  | Eligible Basis | [6 empty] | 70% NPV - 9% or | 30% NPV - 4% |  |  |  | Identify sources and whether grants or loans, if loans, identify rates and terms.
Mortgagor's-LIHTC Cost Certification | [8 empty] | 70% NPV - 9% or | 30% NPV - 4% |  |  |  | 70% NPV - 9% or |  | 30% NPV - 4% |  |  |  |  | 30% NPV - 4% | Existing Building | 1. Total qualified residential units (From I.A) | 0 | units
[9 empty] | 30% NPV - 4% | Existing Building | Bond Basis |  |  | 30% NPV - 4% |  | Existing Building |  | Bond Basis |  |  | New / Rehab | Acquisition | 2. Total market residential units (From I. B) | 0 | units
[8 empty] | ACTUAL COSTS | New / Rehab | Acquisition | 4% Credit |  | ACTUAL COSTS | New / Rehab |  | Acquisition |  | 4% Credit | Totals from Line 36, page 3 |  | 0 | 0 | 3. Total residential units (Lines 1 + 2) | 0 | units
[7 empty] | 1. Construction | [15 empty] | 4. Total low-income residential floor space (From I. A) | 0 | Sq. Ft. |  |  |  |  | Non-qualifying Units
OWNER: | [6 empty] | Site & Improvements | 0 | 0 | 0 | 0 | Total Construction Costs | 0 | 0 |  | 0 |  | 0 | Less Portion of federal grant used to finance |  |  |  | 5. Total market residential floor space (From I. B) | 0 | Sq. Ft.
OWNER MAILING ADDRESS: | [6 empty] | General Requirements | 0 | 0 | 0 | 0 | [7 empty] | qualifying costs. List grants: NRC, City HOME, City Lead |  |  |  | 6. Total residential square footage (Lines 4 + 5) | 0 | Sq. Ft. |  |  |  |  | Non-qualifying units of higher quality is based on the "average quality standard" which is measured by costs per square foot. If the differential between the square foot cost for any non-low income unit and the average square foot cost for all low-income units is greater than 15%, then the entire cost of the non-low income unit is excluded from eligible basis. Please use the following formula:
TAX PAYER IDENTIFICATION NUMBER (LP/ LLC): | [6 empty] | Overhead and Profit | 0 | 0 | 0 | 0 | [11 empty] | 7. Applicable Fraction (units): | #DIV/0!
DEVELOPMENT NAME: | [6 empty] | Building Permits and Other Development Fees | 0 | 0 | 0 | 0 | 6. Developer's Fees |  |  |  | 0 |  | 0 | Less: amount of non-qualified nonrecourse finance |  |  |  | 8. Applicable Fraction (square foot) | #DIV/0!
CHFA MORTGAGE NO: |  |  |  |  | CHFA LIHTC NO. |  | Bond Premium/ L.O.C. Cost | 0 | 0 | 0 | 0 | [11 empty] | 9. Applicable Fraction (lesser of Line 7 or Line 8): | #DIV/0!
ADDRESS OF PROJECT: | [11 empty] | 7. Predevelopment Financing (interest) Costs | 0 | 0 |  | 0 |  | 0 | Less non-qualifying units of higher quality | [10 empty] | 1. | Square foot cost of non-low income unit |  | $
NUMBER OF BUILDINGS: |  |  | TYPE OF CONST. (i.e. stick built, modular, etc.): |  |  |  | Subtotal | 0 | 0 | 0 | 0 | [11 empty] | V. CALCULATING THE QUALIFIED BASIS | [6 empty] | 2. | Average square foot cost of qualified unit |  | $
PLACED IN SERVICE DATE: | [11 empty] | 8. Site Acquisition | [6 empty] | Less non-qualifying excess portion of higher | [10 empty] | 3. | Difference (line 1 minus 2) |  | $
PREPARING CPA FIRM NAME & ADDRESS: | [6 empty] | 2. Contingency |  |  |  |  | Land† |  | XXXXXXXXXXX |  | XXXXXXXXXXX |  | 0 | quality units |  |  |  | 1. Applicable fraction (IV. Line 9) | #DIV/0! | [5 empty] | 4. | Percentage (line 3 line 1) |  |  | %
CPA'S PHONE NUMBER: |  |  |  | E-MAIL: |  |  | Construction Contingency | 0 | 0 | 0 | 0 | Existing Structures, | 0 | XXXXXXXXXXX |  | 0 |  | 0 |  |  |  |  | 2. Eligible basis New Construction/Rehab (page 4) | 0 | [6 empty] | If line 4 is greater than 15%, then do
[19 empty] | Less Historic Tax Credit |  |  |  | 3. Eligible basis Acquisition (page 4) (if applicable) | 0 | [6 empty] | following computation:
[7 empty] | Total Construction | 0 | 0 | 0 | 0 | Subtotal | 0 | 0 |  | 0 |  | 0 |  |  |  |  | 4. Qualified basis New Construction/Rehab (line 1 times line 2) | #DIV/0!
[19 empty] | Less Commercial Space |  |  |  | 5. Qualified basis Acquisition (line 1 times line 3) | #DIV/0! | [5 empty] | A. | Total costs per non-qualifying non-low income unit |  | $
I. BUILDING AND RENTAL DESCRIPTION | [6 empty] | Other: FF&E |  |  | 0 | 0 | 9. Capitalized Reserves
[7 empty] | Other: Commercial Construction |  | XXXXXXXXXXXXX |  | 0 | Operating/Debt Service Reserve† | 0 | XXXXXXXXXXX |  | XXXXXXXXXXX |  | 0 | Qualified Census Tract / Difficult to Develop Area (Yes or No) |  |  |  | VI. THRESHOLD TEST FOR REHAB CREDIT | [6 empty] | B. | Multiplied by number of non-low income units
A. Qualified Residential Rental Units: | [6 empty] | Other: Owner's Change Orders |  | XXXXXXXXXXXXX |  | 0 | Investor Required Reserve† | 0 | XXXXXXXXXXX |  | XXXXXXXXXXX |  | 0 | [12 empty] | with the differential |  | $
[12 empty] | Other (Specify) | 0 | XXXXXXXXXXX |  | XXXXXXXXXXX |  | 0 | Multiplied by 130%, if applicable (see footnote 2 ) |  | N/A | XXXXXXXXXXXX | In order to perform this test, project the number of units and square footage to be occupied by low-income individuals
|  |  | Net |  |  |  | Subtotal | 0 | 0 | 0 | 0 | Other (Specify) | 0 | XXXXXXXXXXX |  | XXXXXXXXXXX |  | 0 |  |  |  |  | at the end of the first taxable year in which the credit is claimed. | [6 empty] | C. | Total cost to be deducted from eligible basis
| No. of | Size in Sq. | Residential | Gross | Utility | Net Tenant | [12 empty] | Total Eligible Basis |  | 0 | 0 | [8 empty] | (line A x line B). |  | $
| Units | Ft.¨ | Sq. Ft. | Tenant Rent | Allowance. | Rent | 3. Architectural and Engineering Fees |  |  |  |  | Subtotal | 0 | 0 |  | 0 |  | 0 |  |  |  |  | 1. Number of Qualified Units: | 0
1-Bedroom |  |  | 0 | 0 | 0 | 0 | Architect Fee-Design | 0 | 0 | 0 | 0 | [11 empty] | 2. Amount of Low-Income Occupied Square Footage: | 0 | [5 empty] | Non-qualifying Excess Portion of Higher Quality Units
1-Bedroom |  |  | 0 | 0 | 0 | 0 | Architect Fee-Supervision | 0 | 0 | 0 | 0 | TOTAL REPLACEMENT COSTS | 0 | 0 |  | 0 | 0 | 0 | Nonqualified nonrecourse financing means any nonrecourse financing (as defined in Section 49 (a)(1)(D)(iii) of the code that is not qualified. Qualified nonrecourse financing means any financing with respect to any property if: (1) such property is acquired by the taxpayer from a person who is not a related person (as defined in Section 49(a)(1)(D)(iv) of the code); (ii) the amount of nonrecourse financing with respect to such property does not exceed 80% of the credit base of such property, and (iii) such financing is borrowed from a qualified person or represents a loan from or guaranteed to any federal state or local government instrumentality thereof. If the "Average Quality Standard" of the low-income units is significantly lower than that for non-low income units, then the entire "tax credit value" of the non-low income units is deducted in computing the credits. See page 7 for determination formula with higher quality. If the "Average Quality Standard" of the low income unites is not significantly lower than that for non-low income units then those costs representing the differential amount are excluded from basis. See page 7 for determination formula. |  |  |  | 3. Applicable Fraction (units): Line 1 divided by total number of residential units | #DIV/0!
2-Bedroom |  |  | 0 | 0 | 0 | 0 | Engineering Fees | 0 | 0 | 0 | 0 | [11 empty] | 4. Applicable Fraction (square foot): Line 2 divided by total number if residential units | #DIV/0! | [5 empty] | If the differential between the square foot cost for all qualified units in a building is not more than 15 percent, then only costs representing the differential amount are excluded from the eligible basis, if the owner elects to do this.
2-Bedroom |  |  | 0 | 0 | 0 | 0 | Surveys | 0 | 0 | 0 | 0 | 10. Entity and Syndication Costs | [10 empty] | 5. Applicable Fraction: (lesser of Line 3 or 4) | #DIV/0!
2-Bedroom |  |  | 0 | 0 | 0 | 0 | Other (Specify): | 0 | 0 | 0 | 0 | Entity Organizational and Legal† | 0 | XXXXXXXXXXX |  | XXXXXXXXXXX |  | 0 |  |  |  |  | 6. Qualified Basis for Rehab Credit, (pg. 4) times line 5 | #DIV/0!
2-Bedroom |  |  | 0 | 0 | 0 | 0 | Other (Specify): | 0 | 0 | 0 | 0 | Syndication Fees/ Commissions† | 0 | XXXXXXXXXXX |  | XXXXXXXXXXX |  | 0 |  |  |  |  | 7. Threshold test for Rehab credit: Line 6 divided by Line 1. | #DIV/0! | [5 empty] | 1. | Square foot cost of non-low income unit |  | $
3-Bedroom |  |  | 0 | 0 | 0 | 0 | Other (Specify): | 0 | 0 | 0 | 0 | Equity Bridge Loan Interest and Fees† | 0 | XXXXXXXXXXX |  | XXXXXXXXXXX |  | 0 |  |  |  |  | This amount must be at least equal to the greater of $3,000 per qualified unit or not less than 10% of the adjusted basis of the building | [6 empty] | 2. | Average square foot cost of qualified unit |  | $
3-Bedroom |  |  | 0 | 0 | 0 | 0 | Other (Specify): | 0 | 0 | 0 | 0 | Tax Opinion and Entity Accounting† | 0 | XXXXXXXXXXX |  | XXXXXXXXXXX |  | 0 | [11 empty] | 3. | Difference (line 1 minus 2) |  | $
3-Bedroom |  |  | 0 | 0 | 0 | 0 | [5 empty] | CHFA Tax Credit Fee† | 0 | XXXXXXXXXXX |  | XXXXXXXXXXX |  | 0 | [7 empty] | TOTAL |  | 0 |  | 4. | Percentage (line 3 line 1) |  |  | %
3-Bedroom |  |  | 0 | 0 | 0 | 0 | Subtotal: | 0 | 0 | 0 | 0 | CHFA LIHTC Fee or Fed. Historic Credit app † | 0 | XXXXXXXXXXX |  | XXXXXXXXXXX |  | 0 | [12 empty] | If line 4 is greater than 15%, then do
3-Bedroom |  |  | 0 | 0 | 0 | 0 | [5 empty] | Other (Specify): | 0 | XXXXXXXXXXX |  | XXXXXXXXXXX |  | 0 | [7 empty] | (discount rate basis: |  | % |  |  | following computation:
3-Bedroom |  |  | 0 | 0 | 0 | 0 | 4. Finance and Interim Costs | [15 empty] | VII. CALCULATING THE HOUSING CREDIT DOLLAR AMOUNTS
4-Bedroom |  |  | 0 | 0 | 0 | 0 | Interest - Construction Loan | 0 | 0 | 0 | 0 | Subtotal† | 0 | 0 |  | 0 | [13 empty] | A. | Total square foot cost non-low income unit
4-Bedroom |  |  | 0 | 0 | 0 | 0 | Perm Loan Orig./Commit Fee | 0 | 0 | XXXXXXXXXXXXX | 0 | [11 empty] | 1. Qualified basis for New Construction/Rehab (Section IV, Line 4) | #DIV/0! |  | THE FOLLOWING DOCUMENTATION MUST ACCOMPANY THIS COST CERTIFICATION: |  |  |  |  | which is equal or less than 15% differential |  | $
4-Bedroom |  |  | 0 | 0 | 0 | 0 | Interest - Bridge Loan | 0 | 0 | 0 | 0 | [11 empty] | 2. Qualified basis for Acquisition (Section IV, Line 5) | #DIV/0!
4-Bedroom |  |  | 0 | 0 | 0 | 0 | Fees - Bridge Loan | 0 | 0 | 0 | 0 | 11. Total Uses | 0 | 0 |  | 0 |  | 0 |  |  |  |  | 3. Applicable percentage rate for New Construction / Rehab* | 9% |  | 1) DOCUMENTATION OF FINANCING, i.e., COPIES OF MORTGAGE NOTES AND/OR MORTGAGE DEEDS. |  |  |  | B. | Multiplied by number of non-low income units
4-Bedroom |  |  | 0 | 0 | 0 | 0 | Real Estate Taxes/Pilots | 0 | 0 | 0 | 0 | [11 empty] | 4. Month and year of applicable percentage rate for New Construction / Rehab | 0 | [6 empty] | with the differential |  | $
Total | 0 |  | 0 |  |  |  | Insurance | 0 | 0 | 0 | 0 | [11 empty] | 5. Applicable percentage rate for Acquisition* | 0% |  | 2) DOCUMENTATION OF THE SYNDICATION AGREEMENT, i.e., FUNDING AGREEMENT OF OTHER
[7 empty] | Utilities | 0 | 0 | 0 | 0 | † Any costs not subject to depreciation are not includable in eligible basis. | [10 empty] | 6. Month and year of applicable percentage rate for Acquisition | 0 |  | AGREEMENT SETTING FOR THE PARAMETERS OF THE DEAL. |  |  |  | C. | Total cost to be deducted from eligible basis
Type of rent subsidies, if applicable: | [6 empty] | Cost of Bond Issuance | 0 | XXXXXXXXXXXXX | XXXXXXXXXXXXX | 0 | Please refer to Sec. 42(d)(2) as to whether or not acquisition costs can be included in eligible basis. | [10 empty] | 7. Credit amount for New Construction/Rehab (Line 1 times Line 3) | #DIV/0! | [6 empty] | (line A x line B). |  | $
[7 empty] | Other (Specify) | 0 | 0 | 0 | 0 | [11 empty] | 8. Credit amount for Acquisition (Line 2 times Line 4) | #DIV/0! |  | 3) A COPY OF THE CERTIFICATE(S) OF OCCUPANCY.
[7 empty] | Other (Specify) | 0 | 0 | 0 | 0 | [11 empty] | 9. Total amount of annual credit (Line 7 + Line 8) | #DIV/0!
B. Market Residential Rental Units: | [6 empty] | Other (Specify) | 0 | 0 | 0 | 0 | 50% Test Calculation | [10 empty] | 10. 10-year credit (Line 9 times 10) | #DIV/0! |  | To the best of my (our) knowledge and belief, no information contained in this Form is in any way false or incorrect, and the information contained within is truly descriptive of the project and or property for which the Low-Income Housing Tax Credits are being applied.
[7 empty] | Construction Observation | 0 | 0 | 0 | 0 | Bond Amount | 0 | [9 empty] | 11. Equity price | 0
|  |  | Net | [8 empty] | Aggregate Basis | 0 | #DIV/0! | % of the project’s aggregate basis financed by volume cap Tax-Exempt Bonds | [7 empty] | 12. Estimated LIHTC Net Proceeds | #DIV/0!
| No. of | Size in Sq. | Residential | Gross | Utility | Net Tenant | Subtotal: | 0 | 0 | 0 | 0 | [14 empty] | Owner: | [Insert Name of Owner Entity]
| Units | Ft.¨ | Sq. Ft. | Tenant Rent | Allowance. | Rent | [16 empty] | * Use the percentage rate prescribed by the Treasury for the month that your building was placed in service unless you made an election to the contrary in your Carryover Allocation Agreement. All projects that benefit from a federal subsidy (a loan or obligation of federal funds where the interest rate on the loan or obligation is less than the prevailing treasury interest rates) or tax-exempt financing provided by state or local governments are eligible for the 30% annual credit.
0-Bedroom | 0 | 0 | 0 | 0 | 0 | 0 | 5. Soft Costs - Fees & Expenses
1-Bedroom | 0 | 0 | 0 | 0 | 0 | 0 | Legal Counsel - Real Estate* | 0 | 0 | 0 | 0 | [14 empty] | [Insert Authorized Signatory Name and Title] |  |  | Date
2-Bedroom | 0 | 0 | 0 | 0 | 0 | 0 | External Legal Counsel | 0 | 0 | 0 | 0
3-Bedroom | 0 | 0 | 0 | 0 | 0 | 0 | Title Insurance Premiums and Recording Costs | 0 | 0 | 0 | 0
Total | 0 |  | 0 |  |  |  | Appraisal/Market Study | 0 | 0 | 0 | 0
[7 empty] | Lease-Up & Marketing | 0 | XXXXXXXXXXXXX | XXXXXXXXXXXXX | 0 | [7 empty] | 2Please Note: The 130% is relevant to projects in a HUD designated difficult development and/or qualified census tract area. | [6 empty] | Duly Authorized
¨ If you have multiple sizes in a unit type please calculate the average. | [6 empty] | Cost Certification [CHFA/LIHTC Required] | 0 | XXXXXXXXXXXXX | XXXXXXXXXXXXX | 0 | [7 empty] | This provision does not apply to acquisition basis in accordance with the Code.
The Utility Allowance is subtracted from the gross tenant rent to arrive at the net tenant rent. | [6 empty] | Environmental Reports and Testing | 0 | 0 | 0 | 0
[7 empty] | Relocation | 0 | XXXXXXXXXXXXX | XXXXXXXXXXXXX | 0
COMMERCIAL SPACE USAGE: | [6 empty] | Other (Specify): | 0 | 0 | 0 | 0 | [14 empty] | STATE OF__________________________
[7 empty] | Other (Specify): | 0 | 0 | 0 | 0 | [14 empty] | COUNTY OF________________________ |  |  | SS: ____________________________
C. Commercial Space: |  |  | Gross Sq. Ft. | 941 | Net Sq. Ft. | 0 | Soft Cost Contingency | 0 | 0 | 0 | 0
Net Annual Income from Commercial Space: |  |  | $ | 0 |  |  | Subtotal | 0 | 0 | 0 | 0
Notary Public
[7 empty] | * Not to include any legal fees associated with the syndication. | [18 empty] | My commission expires:_______________
Yes
No

## Placed In Service Date Cert.
DEVELOPMENT OWNER’S CERTIFICATION OF PLACED-IN-SERVICE DATE
(A SEPARATE CERTIFICATION IS REQUIRED FOR EACH BUILDING)
Development Name:
Development Address:
CHFA #
Building Identification Number
The undersigned hereby certifies to the Connecticut Housing Finance Authority that the building located at ___________________________ is a qualified low-income housing building in accordance with Section 42 of the Internal Revenue Code of 1986, as amended, (the “Code”) and is eligible for an annual allocation of Low-Income Housing Tax Credits in the amount of $______________.
The undersigned further certifies, pursuant to provisions of Section 42 of the Code, the following:
Date building was placed in service:
Acquisition-existing building (month/day/year):
Rehabilitation (month/day/year):
New construction (month/day/year):
Total Number of low-income units in the building:
Total units in the building :
Total Square footage of Qualified Units in the building: :
Total square footage of all residential units in the building
Eligible basis for the acquisition credit:
Qualified basis for the acquisition credit:
Eligible basis for new construction or rehabilitation:
Qualified basis for new construction or rehabilitation:
First year of the tax credit period:
By:
| Signature | Date
| Name and Title | Date
TAX PAYER IDENTIFICATION NUMBER (LP/ LLC)

## Syndicator Investor Cert
SYNDICATOR OR INVESTOR CERTIFICATION
(Syndicator or Investor Letterhead)
Development Name:
Development Address:
CHFA #
This letter is to advise the Connecticut Housing Finance Authority that __________________________, syndicator of the Low-Income Housing Tax Credits for the above referenced development, has reviewed the attached cost certification dated ______________ as prepared by ______________________________________, an independent certified public accountant. Please be advised that we concur with the development’s sources and uses of funds and all costs represented to be includible in the eligible basis as indicated in the attached cost certification.
In addition, by this letter we are also confirming that the owner of the development has elected to commence the start of the tax credit period in the year ________. Therefore, the owner has chosen (not to)/ (to) defer the start of the tax credit period until the year after the development was placed in service.
Sincerely,

## Request for 8609
REQUEST FOR ISSUANCE OF FORM(S) 8609
Development Name:
Development Address:
CHFA #
This letter is to request the Connecticut Housing Finance Authority to review the attached General Contractor’s and Mortgagor’s-LIHTC Cost Certification for the issuance of the IRS Form(s) 8609.
Please be advised that ________________________________, syndicator of the Low-Income Housing Tax Credits for the above referenced development, has reviewed the attached Cost Certification dated ______________ as prepared by ______________________________________, an independent certified public accountant. The syndicator’s concurrence with the development’s Sources and Uses of Funds and all costs represented to be includible in the Eligible Basis as indicated in the attached Cost Certification is evidenced by the attached Syndicator or Investor Certification.
In addition, by this letter we are also confirming that the mortgagor of the development has elected to commence the start of the tax credit period in the year ________.
Sincerely,

## Total Development Costs (hidden)
TOTAL DEVELOPMENT COSTS
Version 2020.1
CONNECTICUT HOUSING FINANCE AUTHORITY
|  | Development Name: | 0
|  | Development Address: | 0
|  | CHFA Development #: | 0
|  | LIHTC #: | 0
PART A: DEVELOPMENT COSTS |  |  |  |  | TAX CREDIT ELIGIBLE BASIS
A | B | C | D | E | F | G | H | I | J
| DEVELOPMENT BUDGET LINE ITEMS: | CHFA APPROVED DEV. BUDGET AMOUNTS MM/DD/YY | MORTGAGOR'S-LIHTC COST CERTIFIED COSTS | CHFA RECOGNIZED COSTS | DIFFERENCE E LESS C | 70% NPV - 9% OR 30% NPV - 4% (NEW/REHAB) CERTIFIED BASIS | 30% NPV - EXISTING BLDG. ACQUISITION CERTIFIED BASIS | CHFA RECOGNIZED 70% NPV - 9% OR 30% NPV - 4% (NEW/REHAB) BASIS | CHFA RECOGNIZED 30% NPV - EXISTING BLDG. ACQUISITION BASIS
1 | CONSTRUCTION
2 | Site & Improvements | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
3 | General Requirements | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
4 | Overhead and Profit | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
5 | Building Permits and Other Development Fees | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
6 | Bond Premium/ L.O.C. Cost | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7 | SUBTOTAL | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8 | CONTINGENCY
9 | Construction Contingency |  | 0 |  | 0 | 0 | 0 | 0 | 0
10 | TOTAL CONSTRUCTION | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11 | OTHER
12 | Other: FF&E |  | 0 | 0 | 0 | 0 |  | 0
13 | Other: Owner's Change Orders | 0 | 0 | 0 | 0 | XXXXXXXXXXXXX | 0 | XXXXXXXXXXXXX | 0
14 | SUBTOTAL | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15 | ARCHITECTURAL & ENGINEERING
16 | Architect Fee-Design | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
17 | Architect Fee-Supervision | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
18 | Engineering Fees | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
19 | Surveys | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20 | Other (Specify): | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
21 | Other (Specify): | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
22 | Other (Specify): | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
23 | Other (Specify): | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
24 | SUBTOTAL | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
25 | FINANCE & INTERIM COSTS
26 | Interest - Construction Loan | 0 | 0 | 0 | 0 | 0 | 0 | 0
27 | Perm Loan Orig./Commit Fee | 0 | 0 | 0 | 0 | 0 | XXXXXXXXXXXXX | 0
28 | Interest - Bridge Loan | 0 | 0 | 0 | 0 | 0 | 0 | 0
29 | Fees - Bridge Loan | 0 | 0 | 0 | 0 | 0 | 0 | 0
30 | Real Estate Taxes/Pilots
31 | Insurance
32 | Utilities
33 | Cost of Bond Issuance | 0 | 0 | 0 | 0 | 0 | 0 | 0
34 | Other (Specify) | 0 | 0 | 0 | 0 | 0 | 0 | 0
35 | Other (Specify) | 0 | 0 | 0 | 0 | 0 | 0 | 0
36 | Other (Specify) | 0 | 0 | 0 | 0 | 0 | 0 | 0
37 | Construction Observation | 0 | 0 | 0 | 0 | 0 | 0 | 0
38 | SUBTOTAL | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
39 | SOFT COSTS
40 | Legal Counsel - Real Estate* | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
41 | External Legal Counsel | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
42 | Title Insurance Premiums and Recording Costs | 0 | 0 | 0 | 0 | 0 | XXXXXXXXXXXXX | 0 | XXXXXXXXXXXXX
43 | Appraisal/Market Study | 0 | 0 | 0 | 0 | XXXXXXXXXXXXX | XXXXXXXXXXXXX | XXXXXXXXXXXXX | XXXXXXXXXXXXX
44 | Lease-Up & Marketing | 0 | 0 | 0 | 0 | XXXXXXXXXXXXX | 0 | XXXXXXXXXXXXX | 0
45 | Cost Certification [CHFA/LIHTC Required] | 0 | 0 | 0 | 0 | 0 | XXXXXXXXXXXXX | 0 | XXXXXXXXXXXXX
46 | Environmental Reports and Testing | 0 | 0 | 0 | 0 | XXXXXXXXXXXXX | 0 | XXXXXXXXXXXXX | 0
47 | Relocation | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
48 | Other (Specify): |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
49 | Other (Specify): | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
50 | Soft Cost Contingency | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
51 | SUBTOTAL | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
52 | TOTAL DEVELOPMENT COST | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
53 | Developer Allowance / Fee | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
54 | Site Acquisition - Land
55 | Site Acquisition - Existing Structures
56 | Operating/Debt Service Reserve†
57 | Investor Required Reserve† | 0 | 0 | 0 | 0 | XXXXXXXXXXXXX | XXXXXXXXXXX | XXXXXXXXXXXXX | XXXXXXXXXXX
58 | Other (Specify) | 0 | 0 | 0 | 0 | XXXXXXXXXXXXX | 0 | XXXXXXXXXXXXX | 0
59 | Other (Specify) | 0 | 0 | 0 | 0 | XXXXXXXXXXXXX | XXXXXXXXXXXXX | XXXXXXXXXXXXX | XXXXXXXXXXXXX
60 | PART A: TOTAL | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
61 | PART B. SYNDICATION & OTHER COSTS
62 | Entity Organizational and Legal† | 0 | 0 | 0 | 0 | XXXXXXXXXXX | XXXXXXXXXXX | XXXXXXXXXXX | XXXXXXXXXXX
63 | Syndication Fees/ Commissions†
64 | Equity Bridge Loan Interest and Fees†
65 | Tax Opinion and Entity Accounting†
66 | CHFA Tax Credit Fee†
67 | CHFA LIHTC Fee or Fed. Historic Credit app † | 0 | 0 | 0 | 0 | XXXXXXXXXXX | XXXXXXXXXXX | XXXXXXXXXXX | XXXXXXXXXXX
68 | Other (Specify):
69 | PART B TOTAL | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
70 | TOTAL | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | TOTAL COST OVERRUN/(SAVINGS) |  |  | 0
Yes
No
|  | UNITS | S.F. |  |  |  | Rehabilitation | Acquisition | Total
| Qualified Units | 0 | 0 |  |  | Total Basis | 0 | 0 | 0
[6 empty] | Less Historic Tax Credit Basis | 0 | 0 | 0
| Market Rate Units | 0 | 0 |  |  | Less Commercial Space Basis |  |  | 0
[6 empty] | Eligible Basis | 0 | 0 | 0
| Total | 0 | 0 |  |  | QCT / DDA (Select Yes or No) | Yes
| Applicable Fraction | #DIV/0! | #DIV/0! |  |  | QCT / DDA Increment | 0 | XXXXXXXXXXXX
|  | Applicable Fraction | #DIV/0! |  |  | Adjusted Eligible Basis | 0 | 0 | 0
[6 empty] | Applicable Fraction | #DIV/0! | #DIV/0!
[6 empty] | Total Qualified Basis | #DIV/0! | #DIV/0! | #DIV/0!
[6 empty] | AFR | 9%
[6 empty] | Credit Earned | #DIV/0! | #DIV/0! | #DIV/0!
[6 empty] | Original Annual Credit Allocation | 0
| Prepared By: |  | Date
[6 empty] | Increase/(Decrease) in Annual Allocation | #DIV/0!
[6 empty] | Maximum Possible Annual Credit Allocation | #DIV/0!
| Approved By: Joe Voccio, Director, Multifamily |  | Date
Note on E19: Kabir, Mahjabeen: Override formula if the G.C. contract is a stipulated sum (a/k/a fixed-price contract) to accept the contract amount.
Note on E65: Kabir, Mahjabeen: Verify the amount of developer fee from the Limited Partnership or Operating Agreement.
Note on H90: Kabir, Mahjabeen: If applicable, enter negative #
Note on H91: Kabir, Mahjabeen: If applicable, enter negative #
Note on H102: Kabir, Mahjabeen: From 42(m) letter (4%) or Carryover Allocation (9%)

## Tax Credit Gap Analysis (hidden)
Version 2020.1
(LIHTC Cost Certification Review)
CONNECTICUT HOUSING FINANCE AUTHORITY
| Development Name: | 0
| Development Address: | 0
| CHFA Development #: | 0
| LIHTC #: | 0
Anticipated Placed-in-Service Date: |  | Original Annual Credit: | 0
Actual Placed-in-Service Date: | See Building Schedule | Original 10-Year Credit: | 0
LIHTC Placed-in-Service Deadline: |  | Allocation Date: | 0
Tax Credit Price:
|  | Tax Credit Equity: | 0
The completed development consists of:
| Rehabilitated Building(s) | 0
| Qualified Units | 0
| CHFA APPROVED SOURCES | CHFA RECOGNIZED SOURCES | DIFFERENCE
Equity Capital, Grants, Etc.
Federal LIHTC Net Proceeds | 0 | 0 | 0
Other | 0 | 0
Other | 0 | 0
Other | 0 | 0
Other | 0 | 0
Other | 0 | 0
Other | 0 | 0 | 0
Deferred Developer Fee | 0 | 0 | 0
Equity Subtotal | 0 | 0 | 0
Financing
1st Mortgage | 0 | 0 | 0
Other | 0 | 0 | 0
Other | 0 | 0 | 0
Other | 0 | 0 | 0
Other | 0 | 0 | 0
Other | 0 | 0 | 0
Financing Subtotal | 0 | 0 | 0
TOTAL SOURCES | 0 | 0 | 0
CHFA RECOGNIZED COSTS
Costs
Total Construction Costs (Hard Costs) Subtotal |  | 0
Construction Contingency |  | 0
Other: FF&E |  | 0
Other: Owner's Change Orders |  | 0
Architectural and Engineering Subtotal |  | 0
Finance and Interim Costs Subtotal |  | 0
Soft Costs - Fees and Expenses Subtotal |  | 0
Lease Up and Marketing |  | 0
Developer Allowance / Fee |  | 0
Site Acquisition - Land |  | 0
Site Acquisition - Existing Structures |  | 0
Other (Specify) |  | 0
RECOGNIZED LENDING COSTS |  | 0
Entity and Syndication Costs/Other Subtotal |  | 0
TOTAL USES |  | 0
Total Recognized Sources |  | 0
Total Recognized Uses |  | 0
Excess/(Gap) |  | 0
Initial LIHTC Equity Amount |  | 0
LIHTC Equity Increase / (Reduction) |  | 0
Final Recognized LIHTC Equity Amount |  | 0
New Tax Credit Equity |  | 0
Tax Credit Price |  | 0
Term in Years |  | 10
New Annual Credit Amount |  | #DIV/0!
Investor Ownership % |  | 99.99%
8609 Credit @ 100% (from Gap Analysis) |  | #DIV/0!
Maximum Possible Credit Award |  | #DIV/0!
Final CHFA Recognized Annual 9% Credit Allocation |  | #DIV/0!
(lesser of Gap Analysis, Maximum Possible Credit Award, or Original Credit Awarded)
Final CHFA Recognized Annual 4% Credit Allocation
(lesser of Gap Analysis or Maximum Possible Credit Award) |  | #DIV/0!
Prepared By: |  | Date
Approved By: Joe Voccio, Director, Multifamily |  | Date
Note on D14: Kabir, Mahjabeen: 42(m) letter or carryover allocation
Note on B24: Kabir, Mahjabeen: Enter from the underwriting model used for the most recent executed Dev. Budget.
Note on C24: Kabir, Mahjabeen: Enter the CHFA recognized sources from the final underwriting. The eligible basis in the underwriting model must agree with the eligible basis determined in the Recapitulation Sheet. The AFR in the final underwriting must agree with the AFR reflected in the cost certification. The final LIHTC equity amount will be reflected on the Summary Page and the LIHTC_Calc worksheets of the underwriting model.
Note on C48: Kabir, Mahjabeen: This section will be automatically populated from the Recap. sheet
Note on C80: Kabir, Mahjabeen: This is 99.99% of the 100% 8609 credit amount in Cell C81. Therefore, this amount will be less than Cell C81.
Note on C82: Kabir, Mahjabeen: This is 100% of the credit that will be reflected on the Form 8609.

## Adj. for Cost Overrun (Savings) (hidden)
Version 2020.1
ADJUSTMENT(S) for COST OVERRUN/(SAVINGS)
|  | Development Name: | 0
|  | Development Address: | 0
|  | CHFA Development #: | 0
|  | LIHTC #: | 0
CHFA RECOGNIZED SOURCES
|  | CHFA APPROVED DEVELOPMENT BUDGET AMOUNTS as of DATE | CHFA ADJUSTMENTS | SAVINGS ALLOC. NOTE | FINAL CHFA RECOGNIZED AMOUNT
Equity Capital, Grants, Etc.
| Federal LIHTC Net Proceeds | 0 | 0 | (2) | 0
| Other | 0 | 0 |  | 0
| Other | 0 | 0 |  | 0
| Other | 0 | 0 |  | 0
| Other | 0 | 0 |  | 0
| Other | 0 | 0 |  | 0
| Other | 0 | 0 |  | 0
| Deferred Developer Fee | 0 | 0 | (1) | 0
| Equity Sub-Total | 0 | 0 |  | 0
Financing
| 1st Mortgage | 0 | 0 |  | 0
| Other | 0 | 0 |  | 0
| Other | 0 | 0 |  | 0
| Other | 0 | 0 |  | 0
| Other | 0 | 0 |  | 0
| Other | 0 | 0 |  | 0
| Financing Sub-Total | 0 | 0 |  | 0
| TOTAL SOURCES | 0 | 0 |  | 0
CHFA RECOGNIZED USES
|  | CHFA APPROVED DEVELOPMENT BUDGET AMOUNTS as of DATE | CHFA ADJUSTMENTS | SAVINGS ALLOC. NOTE | FINAL CHFA RECOGNIZED AMOUNT | Dev. Fee % Check
| Total Construction Costs (Hard Costs) Subtotal | 0 | 0 |  | 0
| Construction Contingency | 0 | 0 |  | 0 | #DIV/0!
| Other: FF&E | 0 | 0 |  | 0
| Other: Owner's Change Orders | 0 | 0 |  | 0
| Architectural and Engineering Subtotal | 0 | 0 |  | 0
| Finance and Interim Costs Subtotal | 0 | 0 |  | 0
| Soft Costs - Fees and Expenses Subtotal | 0 | 0 |  | 0
| Lease Up and Marketing | 0 | 0 |  | 0
| TOTAL DEVELOPMENT COST | 0 | 0 |  | 0
| Developer Allowance / Fee | 0 | 0 |  | 0
| Site Acquisition - Land | 0 | 0 |  | 0
| Site Acquisition - Existing Structures | 0 | 0 |  | 0
| Other (Specify) | 0 | 0 |  | 0
| RECOGNIZED LENDING COSTS | 0 | 0 |  | 0
| Entity Organizational and Legal | 0 | 0 |  | 0
| Syndicator Fees / Commissions | 0 | 0 |  | 0
| Tax Opinion & Entity Accounting | #REF! | #REF! |  | #REF!
| CHFA LIHTC Tax Credit Fee | #REF! | #REF! |  | #REF!
| Tax Credit Applications Fees | #REF! | #REF! |  | #REF!
| ENTITY and SYNDICATION COSTS/OTHER | #REF! | #REF! |  | #REF!
| TOTAL USES | #REF! | #REF! |  | #REF!
Net overall savings shall be applied in order set forth below to the extent permitted by applicable federal and/or state law.
1. If a surplus of funds exists due to an overall cost savings, CHFA will first reduce the deferred developer fee.
2. After the reduction of the deferred developer fee, any remaining balance will be applied to reduce the tax credit allocation amount.
3. Any excess syndication proceeds to the multifamily rental housing development above the amount reflected in the development budget approved at the time of initial closing shall be applied, as determined by CHFA, one hundred percent (100%) to benefit the multifamily rental housing development or to CHFA and/or any governmental agency to reduce the principal amounts of their respective mortgage loans as their interests may appear.
| Prepared By: |  |  |  | Date
| Approved By: Joe Voccio, Director, Multifamily |  |  |  | Date
Note on G38: Kabir, Mahjabeen: CHFA recognized developer's fee cannot exceed 15% of TDC. This cell has conditional formatting. If the total % exceeds 16%, this cell will be highlighted in Red.

## Bldg Sched Rehab-NC Credit
Version 2020.1
REHAB - NEW CONSTRUCTION CREDITS
Development Name: | 0
CHFA # | 0
Number of Bldg. | 0
CHFA USE ONLY
[13 empty] | Rehab Credit per CHFA | #DIV/0!
Address | Building I.D. Number | Set Aside Selection | Number of Units | Square Footage | Placed in Service Date | Eligible Basis | Basis Boost (if applicable) | Adjusted Qualified Basis | Applicable Fraction | Qualified Basis | Tax Credit Percentage | Annual Credit Amount Per Building | Credit Per Bldg. % | Annual Credit Allocation per CHFA | Qualified Basis for 8609
[8 empty] | 0 | #DIV/0! | #DIV/0! |  | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | Yes
[8 empty] | 0 | #DIV/0! | #DIV/0! |  | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
[8 empty] | 0 | #DIV/0! | #DIV/0! |  | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
[8 empty] | 0 | #DIV/0! | #DIV/0! |  | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | No
[8 empty] | 0 | #DIV/0! | #DIV/0! |  | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
[8 empty] | 0 | #DIV/0! | #DIV/0! |  | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | 20-50
[8 empty] | 0 | #DIV/0! | #DIV/0! |  | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | 40-60
[8 empty] | 0 | #DIV/0! | #DIV/0! |  | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
[8 empty] | 0 | #DIV/0! | #DIV/0! |  | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
[8 empty] | 0 | #DIV/0! | #DIV/0! |  | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
[8 empty] | 0 | #DIV/0! | #DIV/0! |  | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
[8 empty] | 0 | #DIV/0! | #DIV/0! |  | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
[8 empty] | 0 | #DIV/0! | #DIV/0! |  | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
[8 empty] | 0 | #DIV/0! | #DIV/0! |  | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
[8 empty] | 0 | #DIV/0! | #DIV/0! |  | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
[8 empty] | 0 | #DIV/0! | #DIV/0! |  | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
[8 empty] | 0 | #DIV/0! | #DIV/0! |  | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
[8 empty] | 0 | #DIV/0! | #DIV/0! |  | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
[8 empty] | 0 | #DIV/0! | #DIV/0! |  | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
[8 empty] | 0 | #DIV/0! | #DIV/0! |  | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
[8 empty] | 0 | #DIV/0! | #DIV/0! |  | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
[8 empty] | 0 | #DIV/0! | #DIV/0! |  | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
[8 empty] | 0 | #DIV/0! | #DIV/0! |  | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
[8 empty] | 0 | #DIV/0! | #DIV/0! |  | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
[8 empty] | 0 | #DIV/0! | #DIV/0! |  | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
[8 empty] | 0 | #DIV/0! | #DIV/0! |  | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
[8 empty] | 0 | #DIV/0! | #DIV/0! |  | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
[8 empty] | 0 | #DIV/0! | #DIV/0! |  | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
[8 empty] | 0 | #DIV/0! | #DIV/0! |  | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
[8 empty] | 0 | #DIV/0! | #DIV/0! |  | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
[8 empty] | 0 | #DIV/0! | #DIV/0! |  | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
[8 empty] | 0 | #DIV/0! | #DIV/0! |  | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
[8 empty] | 0 | #DIV/0! | #DIV/0! |  | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
[8 empty] | 0 | #DIV/0! | #DIV/0! |  | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
[8 empty] | 0 | #DIV/0! | #DIV/0! |  | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
[8 empty] | 0 | #DIV/0! | #DIV/0! |  | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
[8 empty] | 0 | #DIV/0! | #DIV/0! |  | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
[8 empty] | 0 | #DIV/0! | #DIV/0! |  | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
[8 empty] | 0 | #DIV/0! | #DIV/0! |  | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
[8 empty] | 0 | #DIV/0! | #DIV/0! |  | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
[8 empty] | 0 | #DIV/0! | #DIV/0! |  | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
[8 empty] | 0 | #DIV/0! | #DIV/0! |  | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
[8 empty] | 0 | #DIV/0! | #DIV/0! |  | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
[8 empty] | 0 | #DIV/0! | #DIV/0! |  | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
[8 empty] | 0 | #DIV/0! | #DIV/0! |  | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
[8 empty] | 0 | #DIV/0! | #DIV/0! |  | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
[8 empty] | 0 | #DIV/0! | #DIV/0! |  | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
[8 empty] | 0 | #DIV/0! | #DIV/0! |  | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
SUBTOTAL: |  |  | 0 | 0 |  | 0 |  | 0 |  | #DIV/0! |  | #DIV/0! |  | #DIV/0! | #DIV/0!
Note on O11: Kabir, Mahjabeen: For transactions with multiple buildings, the CHFA reviewer must ensure that the grand total of annual credit not exceed the annual credit amount in Cell O9.

## Bldg Sched-ACQ Credit
Version 2020.1
ACQUISATION CREDIT
Project Name: | 0
CHFA # | 0
Number of Bldg. | 0
CHFA USE ONLY
[12 empty] | Acquisition Credit per CHFA | #DIV/0!
Address | Building I.D. Number | Set Aside Selection | Number of Units | Square Footage | Placed in Service Date | Eligible Basis | Applicable Fraction | Qualified Basis | Tax Credit Percentage | Annual Credit Amount Per Building | Credit Per Bldg. % | Annual Credit Allocation per CHFA | Qualified Basis for 8609
[7 empty] | #DIV/0! | #DIV/0! |  | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | Yes
[7 empty] | #DIV/0! | #DIV/0! |  | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | No
[7 empty] | #DIV/0! | #DIV/0! |  | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
[7 empty] | #DIV/0! | #DIV/0! |  | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
[7 empty] | #DIV/0! | #DIV/0! |  | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
[7 empty] | #DIV/0! | #DIV/0! |  | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
[7 empty] | #DIV/0! | #DIV/0! |  | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
[7 empty] | #DIV/0! | #DIV/0! |  | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
[7 empty] | #DIV/0! | #DIV/0! |  | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
[7 empty] | #DIV/0! | #DIV/0! |  | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
[7 empty] | #DIV/0! | #DIV/0! |  | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
[7 empty] | #DIV/0! | #DIV/0! |  | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
[7 empty] | #DIV/0! | #DIV/0! |  | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
[7 empty] | #DIV/0! | #DIV/0! |  | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
[7 empty] | #DIV/0! | #DIV/0! |  | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
[7 empty] | #DIV/0! | #DIV/0! |  | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
[7 empty] | #DIV/0! | #DIV/0! |  | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
[7 empty] | #DIV/0! | #DIV/0! |  | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
[7 empty] | #DIV/0! | #DIV/0! |  | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
[7 empty] | #DIV/0! | #DIV/0! |  | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
[7 empty] | #DIV/0! | #DIV/0! |  | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
[7 empty] | #DIV/0! | #DIV/0! |  | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | No
[7 empty] | #DIV/0! | #DIV/0! |  | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
[7 empty] | #DIV/0! | #DIV/0! |  | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | 20-50
[7 empty] | #DIV/0! | #DIV/0! |  | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | 40-60
[7 empty] | #DIV/0! | #DIV/0! |  | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
[7 empty] | #DIV/0! | #DIV/0! |  | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
[7 empty] | #DIV/0! | #DIV/0! |  | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
[7 empty] | #DIV/0! | #DIV/0! |  | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
[7 empty] | #DIV/0! | #DIV/0! |  | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
[7 empty] | #DIV/0! | #DIV/0! |  | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
[7 empty] | #DIV/0! | #DIV/0! |  | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
[7 empty] | #DIV/0! | #DIV/0! |  | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
[7 empty] | #DIV/0! | #DIV/0! |  | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
[7 empty] | #DIV/0! | #DIV/0! |  | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
[7 empty] | #DIV/0! | #DIV/0! |  | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
[7 empty] | #DIV/0! | #DIV/0! |  | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
[7 empty] | #DIV/0! | #DIV/0! |  | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
[7 empty] | #DIV/0! | #DIV/0! |  | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
[7 empty] | #DIV/0! | #DIV/0! |  | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
[7 empty] | #DIV/0! | #DIV/0! |  | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
[7 empty] | #DIV/0! | #DIV/0! |  | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
[7 empty] | #DIV/0! | #DIV/0! |  | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
[7 empty] | #DIV/0! | #DIV/0! |  | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
[7 empty] | #DIV/0! | #DIV/0! |  | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
SUBTOTAL: |  |  | 0 | 0 |  | 0 | #DIV/0! | #DIV/0! |  | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
Note on M9: Kabir, Mahjabeen: For transactions with multiple buildings, the CHFA reviewer must ensure that the grand total of annual credit allocation does not exceed the annual credit allocation in Cell M9.

## Subst. Compl Let 9-24-13 (hidden)
Date
Mortgagor
Attention:
Re: Property Name
Property Address
City, State, Zip Code
Dear Mr. or Ms.,
CHFA has established _______________ as the date of Substantial Completion for the above-referenced project.
____________ (the "Mortgagor") should use the date of Substantial Completion as the cost certification cut-off date;
however, you may use any date which falls between that date and the date of the Mortgagor /LIHTC Cost Certification
submission as the cut-off date for the accumulation of interest, real estate taxes and insurance costs. The Mortgagor/LIHTC
Cost Certification must be submitted to this office no later than 90 days after the date of Substantial Completion.
In accordance with the LIHTC Procedures, developments consisting of more than ten units must submit a
cost certification accompanied by a certified public accountant's report in accordance with Section 1.42(a)(5)
of the Treasury Regulations. A cost certification must be completed for the entire development with a
summary of buildings (attached). In addition, all cost certifications must be accompanied by a "General
Contractor's Cost Certification" in a form acceptable to the authority, including a certified public accountants
report.
Submission of the Mortgagor/LIHTC Cost Certification must follow the CHFA Mortgagor/LIHTC Certification form
line items exactly as shown in the enclosed workbook. CHFA's certification line items will follow the Development Budget
acknowledged by the Mortgagor at Initial Closing, unless there is a later CHFA-accepted Development Budget amendment.
In the event the Mortgagor/LIHTC Certification does not comply with CHFA's requirements, it will be
returned to the Mortgagor. For more detailed instructions, refer to the Cost Certification Preparation Guidelines
(attached).
If you have any questions, please don't hesitate to contact Kim Black at (860) 571-4271 or via email at
Kim.Black@CHFA.org.
Sincerely,
Kim Black, Multifamily Development Officer III
/kmb
Attachment
cc:
File/Cost Certification
Mortgage Underwriter
Architect/Cost Analyst
Note on F17: Change the date - refer to Substantial Completion Certificate

## MAX MORTGAGE LTR (hidden)
Version 2020.1
MAXIMUM MORTGAGE LETTER
Date
Mortgagor Entity
Address
Address
Attention: Mr. or Ms.
RE: Development Name, City (the "Development")
CHFA #
Dear:
The Connecticut Housing Finance Authority ("CHFA"), pursuant to the Cost Certification Agreement and Covenant to Comply with C.G.S. Section 8-253a(6) executed in connection with the financing for the Development, has reviewed the Statement of Actual Cost submitted by _____________(the "Mortgagor") and, in reliance thereon, has made certain related determinations as required. Accordingly, CHFA will accept original credit instruments, secured by its mortgages upon the land and property included in the Development, in an amount not to exceed that set forth as the "Final Recognized Amount" below. Approval of the Maximum Mortgage, as stated, is conditioned upon the following:
A supplemental cost certification, prepared by the Mortgagor on Form 2330SUPP-MR07B, must be submitted within 60 days after final closing in order to account for those items of cost on the current certifications which are "to be paid within 45 days after final closing."
All items approved herein are final and incontestable, except for fraud or material misrepresentation on the part of the Mortgagor, as of the date of the final closing of the mortgages.
The Maximum Mortgage and Mortgagor's Equity Investment, as recognized by CHFA, are as follows:
1. | Sources of Funds |  |  | CHFA Approved | CHFA Recognized | Difference
| a) | Equity Subtotal |  | 0 | 0 | 0
| b) | Financing Subtotal |  | 0 | 0 | 0
| Total CHFA Recognized Sources: |  |  | 0 | 0 | 0
2. | Uses of Funds |  |  | CHFA Approved | CHFA Recognized | Difference
| a) | Development Costs |  | 0 | 0 | 0
| b) | Syndication and Other Costs |  | 0 | 0 | 0
| Total CHFA Recognized Uses: |  |  | 0 | 0 | 0
3. | LOAN-TO-VALUE TEST: |  |  | Maximum Mortgage | CHFA Mortgage | LTV
| a. 90% of Recognized Uses (Statutory Limit) |  |  | 0 | 0 | #DIV/0!
| b. 80% of Recognized Uses (CHFA Procedures Limit) |  |  | 0 | 0 | #DIV/0!
CONNECTICUT HOUSING FINANCE AUTHORITY
Completed by: Underwriter |  |  | Date | Reviewed by: Joe Voccio, Director, Multifamily |  | Date
Approved by: Nancy I 'Obrien, Managing Director of Multifamily |  |  |  | Date
ACKNOWLEDGED & ACCEPTED BY MORTGAGOR
[Insert Mortgagor Entity Name]
EXHIBIT 'A' - Contractor's Cost Data Sheet
EXHIBIT 'B' - Recapitulation Sheet
EXHIBIT 'C' - Tax Credit Gap Analysis Sheet
BY: |  |  |  |  | EXHIBIT 'D' - Adjustments for Overrun/(Savings)
ITS: | Name and Title of Authorized Signatory |  |  | Date
Note on B2: Kabir, Mahjabeen: When completed, please remove fills from all cells prior to requesting signatures.

## Supplement Cost Cert. (hidden)
Date
Mortgagor
Attention:
Re: Property Name
Property Address
City, State, Zip Code (the "Development")
Dear Mr. or Ms.,
The Development's final closing occurred on (date of final closing). To date, the
Connecticut Housing Finance Authority ("CHFA") has not received the
Supplemental Cost Certification which (name of mortgagor)
(the "Mortgagor") was to complete and submit per the loan documents.
Pursuant to CHFA Procedures, there can be no release of any portion of the working
capital deposits until this Certification is received by our office.
Notwithstanding the timeframe for submission specified in the Maximum Mortgage
Letter, please deliver to CHFA (to the attention of Ms. Kim Black) the required
Supplemental Cost Certification for the Development, using the enclosed form.
Should the Mortgagor have any questions regarding this requirement, please contact
Ms. Kim Black at (860) 571-4271 or via email at kim.black@chfa.org.
Sincerely yours,
Nancy I. O'Brien, Administrator
Multifamily Housing Development Programs
NIO/kmb
c: Underwriter
J. Landau
K. Black

## Supplemental Cost Certification (hidden)
SUPPLEMENTAL COST CERTIFICATION
To: | Connecticut Housing Finance Authority | CHFA No.:
| 999 West Street | Development Name :
| Rocky Hill, CT 06067-4005 | City/Town :
This Supplemental Cost Certification is made pursuant to the condition listed on the Authority’s approved Maximum Mortgage Letter dated ____________________.
This Supplemental Cost Certification shall serve as verification that all outstanding payables at the time of Final Closing (as listed on the Certification of Owner), with the exception of the deferred developer fee, if any, have been paid by the Mortgagor and/or the Contractor (as applicable) and that no further amounts are due and owing to any creditors regarding the construction of the above Development.
False statements made herein are punishable under the penalty for false statement as set forth in Connecticut General Statures Section 53a-157b.
Mortgagor's Name |  | Signature
Title |  | Date
General Contractor's Name |  | Signature
Title |  | Date